## HFM Header
HFM Seismic Observer Notes | [8 empty] | Northeast Natural Resources LLC
MIP 5H and 3H
Service Order # |  | DC33-00006 |  |  |  | Logging District: |  | Bradford |  |  | Sales |  | M. Thomas |  |  | Start Date: |  | 2015-10-27
Engineer: |  | F. Richardson / M. Dillon |  |  |  | Logging Engineer: |  | M. Dillon |  |  | Geophys | Geophys | A. Johansen
Seismic Operator |  | J. Montez |  |  |  | Logging Unit #: |  | 303 |  |  | # Stages |  | 60
Seismic Location: |  | Victoria | [12 empty] | Software
[15 empty] | MW Version |  | 2014
| Job Data |  |  |  |  | Job Time Summary |  |  |  | Revenue |  |  |  |  | Service Pack |  | 5,2
Company | Northeast Natural Resources LLC |  |  |  |  | Leave Base | 2015-10-26 10:00 |  |  | Tool |  |  |  |  | Event Detector |  | 5.7.1
Frac Well | MIP 5H and 3H |  |  |  |  | Start HFM | 2015-10-27 12:00 |  |  | Sei-O |  |  |  |  | Sampling Rate |  | 0.5
Field | Monongalia |  |  |  |  | End HFM | 2015-11-16 12:00 |  |  | Discount
County | Monongalia |  |  |  |  | Return Base | 2015-11-16 12:00 |  |  | Total |  | 410400 |  |  | Tool Data
State | West Virginia |  |  |  |  | Op Time | 1900-01-19 | [7 empty] | Tool Type |  | VSI
[6 empty] | Field Hrs | 1900-01-20 02:00 |  |  | WL |  | 246240 |  | 60% | Number of Levels |  | 12
[10 empty] | DCS |  | 123120 |  | 30% | Shuttle Spacing |  | 100
[10 empty] | WS |  | 41040 |  | 10% | Top Tool Depth |  | 6040
Monitor Well Data |  |  |  |  | Monitor Well Coordinates | [9 empty] | Bottom Tool Depth |  | 7140
Well Name | MIP Science Well |  |  |  | Latitude |  | 39.6089
Permanent Datum: |  | GL | Ft. |  | Longitude |  | -79.9799 | [7 empty] | Toolstring
Elevation of RKB |  | 1088 | Ft. |  | Easting |  | 1833288.7 |  |  | Lost Time |  |  |  |  | EDTC | 9231 | ECH | 9281
Elevation of GL: |  | 1072 | Ft. |  | Northing |  | 404245.6 |  |  | Client Hrs Lost |  |  | 0 |  | AH-199 | 601
Total Depth of Well |  | 7672 | Ft. | [6 empty] | Seismic Hrs Lost |  |  | 0 |  | VSPC | ENP55
Max.Devi: |  | .1* | Deg |  | DTC Sonic Log |  |  |  |  | 3rd Party |  |  | 0 |  | VSCC | ENP22
BHT: |  | 160 | F |  | DTS Sonic Log | [9 empty] | VSIS-1 | ENP233 | VSII-1 | 4027
Bit Size: |  | 8.75 | in. |  | VSP Survey | [9 empty] | VSIS-2 | ENP42 | VSII-2 | ENP50
Mud Weight: |  | 8.4 | lb/gl |  | CBL Log | [9 empty] | VSIS-3 | ENP85 | VSII-3 | ENP87
Casing Size |  | 4.5 | in. | [6 empty] | Service Companies |  |  |  |  | VSIS-4 | ENP58 | VSII-4 | 4063
Casing Weight |  | 11.6 | lb/ft |  | Correlated To: |  | SLB SCMT 9OCT15 |  |  | Frac |  |  | SLB |  | VSIS-5 | ENP41 | VSII-5 | 4031
2nd Casing Size |  | None | in. | [6 empty] | Perforation |  |  | E&P |  | VSIS-6 | 4610 | VSII-6 | 4082
2nd Casing Weight |  | None | lb/ft | [11 empty] | VSIS-7 | ENP214 | VSII-7 | 4080
[15 empty] | VSIS-8 | ENP83 | VSII-8 | ENP46
[15 empty] | VSIS-9 | ENP236 | VSII-9 | 4018
1st Frac Well Data |  |  |  |  | Frac Well Coordinates 5H | [9 empty] | VSIS-10 | ENP194 | VSII-10 | 4003
Well Name | MIP 5H |  |  |  | Latitude |  | 39.6018 | [7 empty] | VSIS-11 | 4593 | VSII-11 | 4017
Permanent Datum: |  |  | Ft. |  | Longitude |  | -79.9762 | [7 empty] | VSIS-12 | 4604 | VSII-12 | 4007
Elevation of RKB |  | 1072 | Ft. |  | Easting |  | 1834336.9 | [7 empty] | Tool String Changes
Elevation of GL: |  |  | Ft. |  | Northing |  | 401674.9 | [7 empty] | EDTC-BB |  | ECH-MKA
Total Depth of Well |  |  | Ft. | [11 empty] | AH-199
Max.Devi: |  |  | Deg |  | Relative Location To Monitor | [9 empty] | VSPC
[5 empty] | Easting |  | 1048.2 | [7 empty] | VSCC
[5 empty] | Northing |  | -2570.7 | [7 empty] | VSIS-1 |  | VSII-1
[5 empty] | Elevation GL | [9 empty] | VSIS-2 |  | VSII-2
[5 empty] | Elevation RKB |  | -16 | [7 empty] | VSIS-3 |  | VSII-3
[15 empty] | VSIS-4 |  | VSII-4
[15 empty] | VSIS-5 |  | VSII-5
2nd Frac Well Data |  |  |  |  | Frac Well Coordinates 3H | [9 empty] | VSIS-6 |  | VSII-6
Well Name | MIP 3H |  |  |  | Latitude |  | 39.6018 | [7 empty] | VSIS-7 |  | VSII-7
Permanent Datum: |  |  | Ft. |  | Longitude |  | -79.9761 | [7 empty] | VSIS-8 |  | VSII-8
Elevation of RKB |  | 1082 | Ft. |  | Easting |  | 1834344.9 | [7 empty] | VSIS-9 |  | VSII-9
Elevation of GL: |  |  | Ft. |  | Northing |  | 401656.6 | [7 empty] | VSIS-10 |  | VSII-10
Total Depth of Well |  |  | Ft. | [11 empty] | VSIA-A
Max.Devi: |  |  | Deg |  | Relative Location To Monitor
[5 empty] | Easting |  | 1056.2
[5 empty] | Northing |  | -2589
Elevation GL
[5 empty] | Elevation RKB |  | -6
Comments:
| AFE #100349-604 |  |  | MIP SW

## Perf Notes 5H
HFM Stage & Perf Summary
Sensor Orientation Shot
VSI Dataset
Source Well
| Event |  | Time |  | Depth | Remarks
Shot - 1
Shot - 2
Shot - 3
Shot - 4
Shot - 5
Shot - 6
Perf Stage - 1 |  |  | Date | 2015-10-28 |  |  | Perf Stage - 2 |  |  | Date | 2015-10-29
VSI Dataset |  | 5H_S1_Re-Perf | Time |  | Event No. |  | VSI Dataset |  | 5H_S2P2 | Time |  | Event No.
Plug | [6 empty] | Plug | 14167
Shot 1 | 14226 |  | 14:22 |  | 37 |  | Shot 1 | 14146 |  | 8:43 |  | 27
Shot 2 | 14206 |  | 14:23 |  | 38 |  | Shot 2 | 14107 |  | 8:44 |  | 28
Shot 3 | 14186 |  | 14:24 |  | 39 |  | Shot 3 | 14067 |  | 8:45 |  | 29
Shot 4 | [6 empty] | Shot 4 | 14038 |  | 8:46 |  | 30
Shot 5 | [6 empty] | Shot 5 | 13988 |  | 8:47 |  | 31
Frac-1 |  |  | Date | 2015-10-28 |  |  | Frac-2 |  |  | Date | 2015-10-29
VSI Dataset |  | 5H_S1F_Real / 5H_S1f_Redo2 | RLDF File |  | 5H_S1F / 5H_S1F_Redo2 |  | VSI Dataset |  | 5H_S2F | RLDF File |  | 5H_S2F
Start Recording |  |  | 10:28 / 15:34 |  |  |  | Start Recording |  |  | 10:22
Event Detection Settings |  |  | 2 / 13 |  |  |  | Event Detection Settings |  |  | 2 / 13
Start Pumping |  |  | 11:11 / 15:37 |  |  |  | Start Pumping |  |  | 10:27
Stop Pumping |  |  | 12:06 / 17:40 |  |  |  | Stop Pumping |  |  | 12:25
Stop Recording |  |  | 12:36 / 18:10 |  |  |  | Stop Recording |  |  | 12:55
Total Number of Events |  |  | 22 / 32 |  |  |  | Total Number of Events |  |  | 217
Perf Stage - 3 |  |  | Date | 2015-10-29 |  |  | Perf Stage - 4 |  |  | Date | 2015-10-29
VSI Dataset |  | 5H_S3P | Time |  | Event No. |  | VSI Dataset |  | 5H_s4P | Time |  | Event No.
Plug | 13969 |  | 13:49 |  | 14 |  | Plug | 13771 |  | 18:18 |  | 6
Perfo | 13948 |  | 13:52 |  | 15 |  | Shot 1 | 13750 |  | 18:19 |  | 7
Perfo | 13909 |  | 13:53 |  | 16 |  | Shot 2 | 13711 |  | 18:20 |  | 8
Perfo | 13869 |  | 13:53 |  | 17 |  | Shot 3 | 13671 |  | 18:21 |  | 9
Perfo | 13830 |  | 13:54 |  | 18 |  | Shot 4 | 13632 |  | 18:21 |  | 10
Perfo | 13790 |  | 13:55 |  | 19 |  | Shot 5 | 13592 |  | 18:23 |  | 11
Frac-3 |  |  | Date | 2015-10-09 |  |  | Frac- 4 |  |  | Date | 2015-10-29
VSI Dataset |  | 5H_S3F | RLDF File |  | 5H_S3F |  | VSI Dataset |  | 5H_S4F | RLDF File |  | 5H_S4F
Start Recording |  |  | 15:08 |  |  |  | Start Recording |  |  | 20:03
Event Detection Settings |  |  | 2 / 13 |  |  |  | Event Detection Settings |  |  | 1.8 / 13
Start Pumping |  |  | 15:09 |  |  |  | Start Pumping |  |  | 20:07
Stop Pumping |  |  | 16:44 |  |  |  | Stop Pumping |  |  | 21:37
Stop Recording |  |  | 17:14 |  |  |  | Stop Recording |  |  | 22:28
Total Number of Events |  |  | 37 |  |  |  | Total Number of Events |  |  | 40
Perf Stage - 5 |  |  | Date | 2015-10-30 |  |  | Perf Stage - 6 |  |  | Date | 2015-10-30
VSI Dataset |  | 5H_S5P | Time |  | Event No. |  | VSI Dataset |  | 5H_S6PReal | Time |  | Event No.
Plug | 13575 |  | 2:16 |  | 45 |  | Plug | 13375 |  | 7:27 |  | 48
Shot 1 | 13552 |  | 2:17 |  | 46 |  | Shot 1 | 13354 |  | 7:28 |  | 49
Shot 2 | 13513 |  | 2:18 |  | 48 |  | Shot 2 | 13315 |  | 7:28 |  | 50
Shot 3 | 13473 |  | 2:19 |  | 49 |  | Shot 3 | 13275 |  | 7:29 |  | 51
Shot 4 | 13438 |  | 2:19 |  | 51 |  | Shot 4 | 13236 |  | 7:30 |  | 52
Shot 5 | 13394 |  | 2:20 |  | 53 |  | Shot 5 | 13201 |  | 7:31 |  | 53
Frac- 5 |  |  | Date | 2015-10-30 |  |  | Frac- 6 |  |  | Date | 2015-10-30
VSI Dataset |  | 5H_S5F | RLDF File |  | 5H_S5F |  | VSI Dataset |  | 5H_S6F | RLDF File |  | 5H_S6F
Start Recording |  |  | 4:05 |  |  |  | Start Recording |  |  | 12:23
Event Detection Settings |  |  | 1.8 / 13 |  |  |  | Event Detection Settings |  |  | 1.8 / 13
Start Pumping |  |  | 4:30 |  |  |  | Start Pumping |  |  | 12:25
Stop Pumping |  |  | 6:18 |  |  |  | Stop Pumping |  |  | 14:20
Stop Recording |  |  | 6:48 |  |  |  | Stop Recording |  |  | 14:40
Total Number of Events |  |  | 132 |  |  |  | Total Number of Events |  |  | 343
Perf Stage - 7 |  |  | Date | 2015-10-30 |  |  | Perf Stage - 8 |  |  | Date | 2015-10-30
VSI Dataset |  | 5H_S7P | Time |  | Event No. |  | VSI Dataset |  | 5H_S8P2 | Time |  | Event No.
Plug | 13177 |  | 15:42 |  | 52 |  | Plug | 12979 |  | 21:32 |  | 247
Perfo | 13158 |  | 15:42 |  | 54 |  | Perfo | 12958 |  | 21:33 |  | 250
Perfo | 13117 |  | 15:43 |  | 55 |  | Perfo | 12919 |  | 21:34 |  | 252
Perfo | 13077 |  | 15:44 |  | 56 |  | Perfo | 12883 |  | 21:35 |  | 253
Perfo | 13038 |  | 15:44 |  | 57 |  | Perfo | 12840 |  | 21:36 |  | 254
Perfo | 12998 |  | 15:45 |  | 58 |  | Perfo | 12800 |  | 21:36 |  | 255
Frac- 7 |  |  | Date | 2015-10-30 |  |  | Frac- 8 |  |  | Date | 2015-10-30
VSI Dataset |  | 5H_S7F | RLDF File |  | 5H_S7F |  | VSI Dataset |  | 5H_S8F | RLDF File |  | 5H_S8F2
Start Recording |  |  | 17:05 |  |  |  | Start Recording |  |  | 22:39
Event Detection Settings |  |  | 1.8 / 13 |  |  |  | Event Detection Settings |  |  | 1.8 / 13
Start Pumping |  |  | 17:14 |  |  |  | Start Pumping |  |  | 02:29
Stop Pumping |  |  | 19:51 |  |  |  | Stop Pumping |  |  | 4:21
Stop Recording |  |  | 20:21 |  |  |  | Stop Recording |  |  | 4:51
Total Number of Events |  |  | 218 |  |  |  | Total Number of Events |  |  | 429
Day
Perf Stage - 9 |  |  | Date | 2015-10-31 |  |  | Perf Stage - 10 |  |  | Date | 2015-10-31
VSI Dataset |  | 5H_S9P | Time |  | Event No. |  | VSI Dataset |  | 5H_S10P | Time |  | Event No.
Plug | 12781 |  | 6:06 |  | 57 |  | Plug | 12583 |  | 11:17 |  | 55
Perfo | 12760 |  | 6:07 |  | 59 |  | Perfo | 12560 |  | 11:18 |  | 57
Perfo | 12721 |  | 6:08 |  | 61 |  | Perfo | 12523 |  | 11:58 |  | 58
Perfo | 12681 |  | 6:09 |  | 62 |  | Perfo | 12483 |  | 11:19 |  | 60
Perfo | 12642 |  | 6:09 |  | 63 |  | Perfo | 12444 |  | 11:20 |  | 63
Perfo | 12602 |  | 6:10 |  | 64 |  | Perfo | 12404 |  | 11:26 |  | 72
Frac- 9 |  |  | Date | 2015-10-31 |  |  | Frac- 10 |  |  | Date | 2015-10-31
VSI Dataset |  | 5H_S9F | RLDF File |  | 5H_S9F |  | VSI Dataset |  | 5H_S10F | RLDF File |  | 5H_S10F
Start Recording |  |  | 8:02 |  |  |  | Start Recording |  |  | 12:20
Event Detection Settings |  |  | 1.8 / 13 |  |  |  | Event Detection Settings |  |  | 1.8 / 13
Start Pumping |  |  | 8:04 |  |  |  | Start Pumping |  |  | 12:25
Stop Pumping |  |  | 9:58 |  |  |  | Stop Pumping |  |  | 14:13
Stop Recording |  |  | 10:28 |  |  |  | Stop Recording |  |  | 14:43
Total Number of Events |  |  | 142 |  |  |  | Total Number of Events |  |  | 383
Perf Stage - 11 |  |  | Date | 2015-10-31 |  |  | Perf Stage - 12 |  |  | Date | 2015-10-31
VSI Dataset |  | 5H_S11P | Time |  | Event No. |  | VSI Dataset |  | 5H_S12P | Time |  | Event No.
Plug | 12385 |  | 15:36 |  | 78 |  | Plug | 12187 |  | 22:07 |  | 51
Perfo | 12364 |  | 15:26 |  | 81 |  | Perfo | 12166 |  | 22:08 |  | 52
Perfo | 12325 |  | 15:27 |  | 82 |  | Perfo | 12127 |  | 22:09 |  | 54
Perfo | 12283 |  | 15:27 |  | 83 |  | Perfo | 12087 |  | 22:09 |  | 55
Perfo | 12246 |  | 15:28 |  | 84 |  | Perfo | 12048 |  | 22:10 |  | 56
Perfo | 12206 |  | 15:28 |  | 86 |  | Perfo | 12008 |  | 22:11 |  | 57
Frac- 11 |  |  | Date | 2015-10-31 |  |  | Frac- 12 |  |  | Date | 2015-10-31
VSI Dataset |  | 5H_S11F | RLDF File |  | 5H_S11F |  | VSI Dataset |  | 5H_S12F | RLDF File |  | 5H_S12F
Start Recording |  |  | 18:23 |  |  |  | Start Recording |  |  | 23:25
Event Detection Settings |  |  | 1.8/13 |  |  |  | Event Detection Settings |  |  | 1.8/13
Start Pumping |  |  | 18:58 |  |  |  | Start Pumping |  |  | 23:28
Stop Pumping |  |  | 20:45 |  |  |  | Stop Pumping |  |  | 1:21
Stop Recording |  |  | 21:22 |  |  |  | Stop Recording |  |  | 1:55
Total Number of Events |  |  | 618 |  |  |  | Total Number of Events |  |  | 545
Perf Stage - 13 |  |  | Date | 2015-11-01 |  |  | Perf Stage - 14 |  |  | Date | 2015-11-01
VSI Dataset |  | 5H_S13P | Time |  | Event No. |  | VSI Dataset |  | 5H_S14P | Time |  | Event No.
Plug | 11989 |  | 3:43 |  | 39 |  | Plug | 11791 |  | 9:41 |  | 55
Perfo | 11970 |  | 3:43 |  | 41 |  | Perfo | 11770 |  | 9:42 |  | 57
Perfo | 11929 |  | 3:44 |  | 42 |  | Perfo | 11728 |  | 9:42 |  | 58
Perfo | 11889 |  | 3:45 |  | 43 |  | Perfo | 11691 |  | 9:43 |  | 59
Perfo | 11850 |  | 3:46 |  | 45 |  | Perfo | 11652 |  | 9:43 |  | 60
Perfo | 11810 |  | 3:46 |  | 46 |  | Perfo | 11612 |  | 9:44 |  | 61
Frac- 13 |  |  | Date | 2015-11-01 |  |  | Frac- 14 |  |  | Date | 2015-11-01
VSI Dataset |  | 5H_S13F | RLDF File |  | 5H_S13F |  | VSI Dataset |  | 5H_S14P | RLDF File |  | 5H_S14P
Start Recording |  |  | 4:54 |  |  |  | Start Recording |  |  | 10:39
Event Detection Settings |  |  | 1.8/13 |  |  |  | Event Detection Settings |  |  | 1.8 / 13
Start Pumping |  |  | 5:13 |  |  |  | Start Pumping |  |  | 10:45
Stop Pumping |  |  | 8:12 |  |  |  | Stop Pumping |  |  | 12:31
Stop Recording |  |  | 8:42 |  |  |  | Stop Recording |  |  | 13:01
Total Number of Events |  |  | 913 |  |  |  | Total Number of Events |  |  | 906
Perf Stage - 15 |  |  | Date | 2015-11-01 |  |  | Perf Stage - 16 |  |  | Date | 2015-11-01
VSI Dataset |  | 5H_S15P | Time |  | Event No. |  | VSI Dataset |  | 5H_S16P | Time |  | Event No.
Plug | 11593 |  | 13:42 |  | 14 |  | Plug | 11395 |  | 18:14 |  | 301
Perfo | 11572 |  | 13:42 |  | 17 |  | Perfo | 11376 |  | 18:14 |  | 304
Perfo | 11533 |  | 13:43 |  | 19 |  | Perfo | 11335 |  | 18:15 |  | 311
Perfo | 11493 |  | 13:44 |  | 20 |  | Perfo | 11295 |  | 18:16 |  | 313
Perfo | 11454 |  | 13:44 |  | 21 |  | Perfo | 11256 |  | 18:17 |  | 315
Perfo | 11412 |  | 13:45 |  | 23 |  | Perfo | 11216 |  | 18:17 |  | 318
Frac- 15 |  |  | Date | 2015-11-01 |  |  | Frac- 16 |  |  | Date | 2015-11-01
VSI Dataset |  | 5H_S15F | RLDF File |  | 5H_S15F |  | VSI Dataset |  | 5H_S16F | RLDF File |  | 5H_S16F_2
Start Recording |  |  | 15:02 |  |  |  | Start Recording |  |  | 19:11
Event Detection Settings |  |  | 1.8 / 13 |  |  |  | Event Detection Settings |  |  | 1.8 / 13
Start Pumping |  |  | 15:15 |  |  |  | Start Pumping |  |  | 21:55
Stop Pumping |  |  | 17:00 |  |  |  | Stop Pumping |  |  | 23:38
Stop Recording |  |  | 17:02 |  |  |  | Stop Recording |  |  | 0:08
Total Number of Events |  |  | 597 |  |  |  | Total Number of Events |  |  | 1088
Perf Stage - 17 |  |  | Date | 2015-11-02 |  |  | Perf Stage - 18 |  |  | Date | 2015-11-02
VSI Dataset |  | 5H_S17P | Time |  | Event No. |  | VSI Dataset |  | 5H_S18P | Time |  | Event No.
Plug | 11197 |  | 0:53 |  | 138 |  | Plug | 10999 |  | 6:17 |  | 78
Perfo | 11176 |  | 0:54 |  | 141 |  | Perfo | 10978 |  | 6:17 |  | 79
Perfo | 11134 |  | 0:55 |  | 144 |  | Perfo | 10939 |  | 6:18 |  | 83
Perfo | 11091 |  | 0:56 |  | 147 |  | Perfo | 10899 |  | 6:19 |  | 86
Perfo | 11058 |  | 0:57 |  | 148 |  | Perfo | 10860 |  | 6:20 |  | 87
Perfo | 11018 |  | 0:58 |  | 151 |  | Perfo | 10826 |  | 6:21 |  | 90
Frac- 17 |  |  | Date | 2015-11-02 |  |  | Frac- 18 |  |  | Date | 2015-11-03
VSI Dataset |  | 5H_S17F | RLDF File |  | 5H_S17F |  | VSI Dataset |  | 5H_S18F | RLDF File |  | 5H_S18F_2
Start Recording |  |  | 2:14 |  |  |  | Start Recording |  |  | 0:15
Event Detection Settings |  |  | 1.8/13 |  |  |  | Event Detection Settings |  |  | 2/13
Start Pumping |  |  | 2:42 |  |  |  | Start Pumping |  |  | 0:47
Stop Pumping |  |  | 4:43 |  |  |  | Stop Pumping |  |  |  |  | 2:52
Stop Recording |  |  | 5:13 |  |  |  | Stop Recording |  |  | 3:32
Total Number of Events |  |  | 985 |  |  |  | Total Number of Events |  |  | 948
Perf Stage - 19 |  |  | Date | 2015-11-03 |  |  | Perf Stage - 20 |  |  | Date | 2015-11-03
VSI Dataset |  | 5H_S19P/5H_S19P_2 | Time |  | Event No. |  | VSI Dataset |  | 5H_S20P | Time |  | Event No.
Plug | 10801 |  | 4:17 |  | 87(file 1) |  | Plug | 10603 |  | 10:49 |  | 116
Perfo | 10780 |  | Missed due to losing WAFE connection |  |  |  | Perfo | 10582 |  | 10:50 |  | 121
Perfo | 10741 |  | 4:31 |  | 28(file 2) |  | Perfo | 10537 |  | 10:50 |  | 122
Perfo | 10701 |  | 4:31 |  | 30 |  | Perfo | 10506 |  | 10:51 |  | 123
Perfo | 10662 |  | 4:32 |  | 32 |  | Perfo | 10464 |  | 10:52 |  | 124
Perfo | 10622 |  | 4:32 |  | 34 |  | Perfo | 10424 |  | 10:52 |  | 125
Frac- 19 |  |  | Date | 2015-11-03 |  |  | Frac- 20 |  |  | Date | 2015-11-03
VSI Dataset |  | 5H_S19F | RLDF File |  | 5H_S19FREAL |  | VSI Dataset |  | 5H_S20F | RLDF File |  | 5H_S20F
Start Recording |  |  | 6:47 |  |  |  | Start Recording |  |  | 11:51
Event Detection Settings |  |  | 1.8 / 13 |  |  |  | Event Detection Settings |  |  | 2.4 / 13
Start Pumping |  |  | 8:00 |  |  |  | Start Pumping |  |  | 11:53
Stop Pumping |  |  | 9:43 |  |  |  | Stop Pumping |  |  | 13:32
Stop Recording |  |  | 10:13 |  |  |  | Stop Recording |  |  | 14:02
Total Number of Events |  |  | 1342 |  |  |  | Total Number of Events |  |  | 943
Perf Stage - 21 |  |  | Date | 2015-11-03 |  |  | Perf Stage - 22 |  |  | Date | 2015-11-03
VSI Dataset |  | 5H_S21P | Time |  | Event No. |  | VSI Dataset |  | 5H_S22P | Time |  | Event No.
Plug | 10405 |  | 14:41 |  | 87 |  | Plug | 10207 |  | 19:09 |  | 86
Perfo | 10384 |  | 14:41 |  | 92 |  | Perfo | 10184 |  | 19:10 |  | 89
Perfo | 10345 |  | 14:42 |  | 98 |  | Perfo | 10152 |  | 19:10 |  | 93
Perfo | 10305 |  | 14:42 |  | 102 |  | Perfo | 10107 |  | 19:11 |  | 98
Perfo | 10266 |  | 14:43 |  | 107 |  | Perfo | 10068 |  | 19:12 |  | 99
Perfo | 10224 |  | 14:44 |  | 112 |  | Perfo | 10028 |  | 19:12 |  | 105
Frac- 21 |  |  | Date | 2015-11-03 |  |  | Frac- 22 |  |  | Date | 2015-11-03
VSI Dataset |  | 5H_S21F | RLDF File |  | 5H_S21F |  | VSI Dataset |  | 5H_S22F | RLDF File |  | 5H_S22F
Start Recording |  |  | 16:04 |  |  |  | Start Recording |  |  | 19:40
Event Detection Settings |  |  | 2.5 / 18 |  |  |  | Event Detection Settings |  |  | 2.5/18
Start Pumping |  |  | 16:16 |  |  |  | Start Pumping |  |  | 20:06
Stop Pumping |  |  | 18:00 |  |  |  | Stop Pumping |  |  | 21:43
Stop Recording |  |  | 18:35 |  |  |  | Stop Recording |  |  | 22:13
Total Number of Events |  |  | 515 |  |  |  | Total Number of Events |  |  | 2509
Perf Stage - 23 |  |  | Date | 2015-11-03 |  |  | Perf Stage - 24 |  |  | Date | 2015-11-04
VSI Dataset |  | 5H_S23P | Time |  | Event No. |  | VSI Dataset |  | 5H_S24P | Time |  | Event No.
Plug | 10019 |  | 22:54 |  | 339 |  | Plug | 9811 |  | 2:53 |  | 139
Perfo | 9988 |  | 22:55 |  | 358 |  | Perfo | 9790 |  | 2:53 |  | 142
Perfo | 9945 |  | 22:55 |  | 365 |  | Perfo | 9751 |  | 2:54 |  | 147
Perfo | 9915 |  | 22:56 |  | 372 |  | Perfo | 9711 |  | 2:55 |  | 149
Perfo | 9870 |  | 22:56 |  | 378 |  | Perfo | 9672 |  | 2:55 |  | 154
Perfo | 9830 |  | 22:57 |  | 282 |  | Perfo | 9640 |  | 2:56 |  | 158
Frac- 23 |  |  | Date | 2015-11-03 |  |  | Frac- 24 |  |  | Date | 2015-11-04
VSI Dataset |  | 5H_S23F | RLDF File |  | 5H_S23F |  | VSI Dataset |  | 5H_S24F3 | RLDF File |  | 5H_S24F3
Start Recording |  |  | 23:37 |  |  |  | Start Recording |  |  | 6:44
Event Detection Settings |  |  | 2.8/18 |  |  |  | Event Detection Settings |  |  | 2.5/18
Start Pumping |  |  | 0:24 |  |  |  | Start Pumping |  |  | 6:53
Stop Pumping |  |  | 1:42 |  |  |  | Stop Pumping |  |  | 8:27
Stop Recording |  |  | 2:12 |  |  |  | Stop Recording |  |  | 8:57
Total Number of Events |  |  | 1165 |  |  |  | Total Number of Events |  |  | 772
Perf Stage - 25 |  |  | Date | 2015-11-04 |  |  | Perf Stage - 26 |  |  | Date | 2015-11-04
VSI Dataset |  | 5H_S25P | Time |  | Event No. |  | VSI Dataset |  | 5H_S26P | Time |  | Event No.
Plug | 9613 |  | 9:32 |  | 19 |  | Plug | 9415 |  | 13:06 |  | 13
Perfo | 9592 |  | 9:32 |  | 20 |  | Perfo | 9394 |  | 13:06 |  | 16
Perfo | 9553 |  | 9:33 |  | 21 |  | Perfo | 9350 |  | 13:07 |  | 19
Perfo | 9513 |  | 9:34 |  | 22 |  | Perfo | 9315 |  | 13:08 |  | 21
Perfo | 9474 |  | 9:34 |  | 24 |  | Perfo | 9276 |  | 13:08 |  | 22
Perfo | 9434 |  | 9:34 |  | 26 |  | Perfo | 9236 |  | 13:09 |  | 24
Frac- 25 |  |  | Date | 2015-11-04 |  |  | Frac- 26 |  |  | Date | 2015-11-04
VSI Dataset |  | 5H_S25F | RLDF File |  | 5H_S25P |  | VSI Dataset |  | 5H_S26F | RLDF File |  | 5H_S26F
Start Recording |  |  | 10:24 |  |  |  | Start Recording |  |  | 14:07
Event Detection Settings |  |  | 2.5 / 18 |  |  |  | Event Detection Settings |  |  | 2.5 / 18
Start Pumping |  |  | 10:26 |  |  |  | Start Pumping |  |  | 14:08
Stop Pumping |  |  | 12:02 |  |  |  | Stop Pumping |  |  | 15:48
Stop Recording |  |  | 12:32 |  |  |  | Stop Recording |  |  | 16:18
Total Number of Events |  |  | 336 |  |  |  | Total Number of Events |  |  | 222
Perf Stage - 27 |  |  | Date | 2015-11-04 |  |  | Perf Stage - 28 |  |  | Date | 2015-11-05
VSI Dataset |  | 5H_S27P | Time |  | Event No. |  | VSI Dataset |  | 5H_S28P | Time |  | Event No.
Plug | 9210 |  | 16:59 |  | 28 |  | Plug | 9019 |  | 0:09 |  | 42
Perfo | 9196 |  | 17:00 |  | 32 |  | Perfo | 8998 |  | 0:09 |  | 43
Perfo | 9157 |  | 17:00 |  | 33 |  | Perfo | 8959 |  | 0:10 |  | 46
Perfo | 9117 |  | 17:01 |  | 35 |  | Perfo | 8919 |  | 0:11 |  | 47
Perfo | 9076 |  | 17:02 |  | 39 |  | Perfo | 8877 |  | 0:11 |  | 49
Perfo | 9040 |  | 17:03 |  | 44 |  | Perfo | 8840 |  | 0:12 |  | 50
Frac- 27 |  |  | Date | 2015-11-04 |  |  | Frac- 28 |  |  | Date | 2015-11-05
VSI Dataset |  | 5H_S27F | RLDF File |  | 5H_S27P |  | VSI Dataset |  | 5H_S28F | RLDF File |  | 5H_S28F
Start Recording |  |  | 18:32 |  |  |  | Start Recording |  |  | 1:28
Event Detection Settings |  |  | 2 / 13 |  |  |  | Event Detection Settings |  |  | 2/13
Start Pumping |  |  | 20:43 |  |  |  | Start Pumping |  |  | 1:41
Stop Pumping |  |  | 22:40 |  |  |  | Stop Pumping |  |  | 3:17
Stop Recording |  |  | 23:13 |  |  |  | Stop Recording |  |  | 3:55
Total Number of Events |  |  | 555 |  |  |  | Total Number of Events |  |  | 450
Perf Stage - 29 |  |  | Date | 2015-11-05 |  |  | Perf Stage - 30 |  |  | Date | 2015-11-05
VSI Dataset |  | 5H_S29P | Time |  | Event No. |  | VSI Dataset |  | 5H_S30P | Time |  | Event No.
Plug | 8821 |  | 5:18 |  | 26 |  | Plug | 8623 |  | 9:36 |  | 11
Perfo | 8800 |  | 5:19 |  | 27 |  | Perfo | 8594 |  | 9:36 |  | 12
Perfo | 8761 |  | 5:20 |  | 28 |  | Perfo | 8563 |  | 9:37 |  | 13
Perfo | 8721 |  | 5:20 |  | 29 |  | Perfo | 8523 |  | 9:37 |  | 14
Perfo | 8682 |  | 5:20 |  | 30 |  | Perfo | 8484 |  | 9:38 |  | 16
Perfo | 8642 |  | 5:21 |  | 32 |  | Perfo | 8444 |  | 9:39 |  | 18
Frac- 29 |  |  | Date | 2015-11-05 |  |  | Frac- 30 |  |  | Date | 2015-11-05
VSI Dataset |  | 5H_S29F | RLDF File |  | 5H_S29F |  | VSI Dataset |  | 5H_S30F | RLDF File |  | 5H_S30F
Start Recording |  |  | 6:29 |  |  |  | Start Recording |  |  | 10:38
Event Detection Settings |  |  | 2 / 13 |  |  |  | Event Detection Settings |  |  | 2 / 13
Start Pumping |  |  | 6:55 |  |  |  | Start Pumping |  |  | 11:33
Stop Pumping |  |  | 8:34 |  |  |  | Stop Pumping |  |  | 13:05
Stop Recording |  |  | 9:04 |  |  |  | Stop Recording |  |  | 13:35
Total Number of Events |  |  | 476 |  |  |  | Total Number of Events |  |  | 280

## Perf Notes 3H
HFM Stage & Perf Summary
Sensor Orientation Shot
VSI Dataset
Source Well
| Event |  | Time |  | Depth | Remarks
Shot - 1
Shot - 2
Shot - 3
Shot - 4
Shot - 5
Shot - 6
Perf Stage - 1 |  |  | Date |  |  |  | Perf Stage - 2 |  |  | Date
VSI Dataset |  |  | Time |  | Event No. |  | VSI Dataset |  |  | Time |  | Event No.
Plug | [6 empty] | Plug
Shot 1 | [6 empty] | Shot 1
Shot 2 | [6 empty] | Shot 2
Shot 3 | [6 empty] | Shot 3
Shot 4 | [6 empty] | Shot 4
Shot 5 | [6 empty] | Shot 5
Frac-1 |  |  | Date |  |  |  | Frac-2 |  |  | Date
VSI Dataset |  |  | RLDF File |  |  |  | VSI Dataset |  |  | RLDF File
Start Recording | [6 empty] | Start Recording
Event Detection Settings | [6 empty] | Event Detection Settings
Start Pumping | [6 empty] | Start Pumping
Stop Pumping | [6 empty] | Stop Pumping
Stop Recording | [6 empty] | Stop Recording
Total Number of Events | [6 empty] | Total Number of Events
Perf Stage - 3 |  |  | Date |  |  |  | Perf Stage - 4 |  |  | Date
VSI Dataset |  |  | Time |  | Event No. |  | VSI Dataset |  |  | Time |  | Event No.
Plug | [6 empty] | Perfo
Perfo | [6 empty] | Perfo
Perfo | [6 empty] | Perfo
Perfo | [6 empty] | Perfo
Perfo | [6 empty] | Perfo
Perfo | [6 empty] | Perfo
Frac-3 |  |  | Date |  |  |  | Frac- 4 |  |  | Date
VSI Dataset |  |  | RLDF File |  |  |  | VSI Dataset |  |  | RLDF File
Start Recording | [6 empty] | Start Recording
Event Detection Settings | [6 empty] | Event Detection Settings
Start Pumping | [6 empty] | Start Pumping
Stop Pumping | [6 empty] | Stop Pumping
Stop Recording | [6 empty] | Stop Recording
Total Number of Events | [6 empty] | Total Number of Events
Perf Stage - 5 |  |  | Date |  |  |  | Perf Stage - 6 |  |  | Date
VSI Dataset |  |  | Time |  | Event No. |  | VSI Dataset |  |  | Time |  | Event No.
Perfo | [6 empty] | Perfo
Perfo | [6 empty] | Perfo
Perfo | [6 empty] | Perfo
Perfo | [6 empty] | Perfo
Perfo | [6 empty] | Perfo
Perfo | [6 empty] | Perfo
Frac- 5 |  |  | Date |  |  |  | Frac- 6 |  |  | Date
VSI Dataset |  |  | RLDF File |  |  |  | VSI Dataset |  |  | RLDF File
Start Recording | [6 empty] | Start Recording
Event Detection Settings | [6 empty] | Event Detection Settings
Start Pumping | [6 empty] | Start Pumping
Stop Pumping | [6 empty] | Stop Pumping
Stop Recording | [6 empty] | Stop Recording
Total Number of Events | [6 empty] | Total Number of Events
Perf Stage - 7 |  |  | Date | 2015-11-08 |  |  | Perf Stage - 8 |  |  | Date | 2015-11-09
VSI Dataset |  | 3H_S7P | Time |  | Event No. |  | VSI Dataset |  | 3H_S8P | Time |  | Event No.
Plug | 12435 |  | 23:10 |  | 39 |  | Plug | 12216 |  | 5:18 |  | 22
Perfo | 12418 |  | 23:12 |  | 40 |  | Perfo | 12194 |  | 5:19 |  | 24
Perfo | 12367 |  | 23:14 |  | 41 |  | Perfo | 12143 |  | 5:32 |  | 27
Perfo | 12325 |  | 23:15 |  | 43 |  | Perfo | 12098 |  | 5:36 |  | 29
Perfo | 12285 |  | 23:17 |  | 44 |  | Perfo | 12058 |  | 5:39 |  | 30
Perfo | 12239 |  | 23:18 |  | 46 |  | Perfo | 12015 |  | 5:42 |  | 31
Frac- 7 |  |  | Date | 2015-11-09 |  |  | Frac- 8 |  |  | Date | 2015-11-09
VSI Dataset |  | 3H_S7F | RLDF File |  | 3H_S7F |  | VSI Dataset |  | 3H_S8F | RLDF File |  | 3H_S8F
Start Recording |  |  | 0:47 |  |  |  | Start Recording |  |  | 6:44
Event Detection Settings |  |  | 1.8/13 |  |  |  | Event Detection Settings |  |  | 1.8 / 13
Start Pumping |  |  | 01:27 |  |  |  | Start Pumping |  |  | 8:14
Stop Pumping |  |  | 3:32 |  |  |  | Stop Pumping |  |  | 10:06
Stop Recording |  |  | 4:06 |  |  |  | Stop Recording |  |  | 10:36
Total Number of Events |  |  | 473 |  |  |  | Total Number of Events |  |  | 376
Perf Stage - 9 |  |  | Date | 2015-11-09 |  |  | Perf Stage - 10 |  |  | Date | 2015-11-09
VSI Dataset |  | 3H_S9P | Time |  | Event No. |  | VSI Dataset |  | 3H_S10P | Time |  | Event No.
Plug | 11993 |  | 12:00 |  | 5 |  | Plug | 11759 |  | 19:13 |  | 15
Perfo | 11971 |  | 12:02 |  | 23 |  | Perfo | 11735 |  | 19:15 |  | 17
Perfo | 11925 |  | 12:04 |  | 25 |  | Perfo | 11695 |  | 19:17 |  | 18
Perfo | 11880 |  | 12:05 |  | 27 |  | Perfo | 11649 |  | 19:19 |  | 22
Perfo | 11828 |  | 12:07 |  | 29 |  | Perfo | 11601 |  | 19:41 |  | 31
Perfo | 11782 |  | 12:09 |  | 31 |  | Perfo | 11557 |  | 19:43 |  | 32
Frac- 9 |  |  | Date | 2015-11-09 |  |  | Frac- 10 |  |  | Date | 2015-11-09
VSI Dataset |  | 3H_S9F | RLDF File |  | 3H_S9F |  | VSI Dataset |  | 3H_S10F | RLDF File |  | 3H_S10F
Start Recording |  |  | 13:51 |  |  |  | Start Recording |  |  | 20:34
Event Detection Settings |  |  | 1.8 / 13 |  |  |  | Event Detection Settings |  |  | 1.8/13
Start Pumping |  |  | 15:49 |  |  |  | Start Pumping |  |  | 20:58
Stop Pumping |  |  | 17:39 |  |  |  | Stop Pumping |  |  | 22:39
Stop Recording |  |  | 18:09 |  |  |  | Stop Recording |  |  | 23:15
Total Number of Events |  |  | 589 |  |  |  | Total Number of Events |  |  | 532
Perf Stage - 11 |  |  | Date | 2015-11-11 |  |  | Perf Stage - 12 |  |  | Date | 2015-11-11
VSI Dataset |  | 3H_S11P | Time |  | Event No. |  | VSI Dataset |  | 3H_S12P | Time |  | Event No.
Plug | 11533 |  | 1:55 |  | 63 |  | Plug | 11301 |  | 6:54 |  | 16
Perfo | 11509 |  | 1:57 |  | 65 |  | Perfo | 11277 |  | 6:55 |  | 18
Perfo | 11457 |  | 1:59 |  | 66 |  | Perfo | 11230 |  | 6:57 |  | 19
Perfo | 11416 |  | 2:00 |  | 67 |  | Perfo | 11187 |  | 6:58 |  | 20
Perfo | 11371 |  | 2:02 |  | 68 |  | Perfo | 11140 |  | 6:59 |  | 22
Perfo | 11324 |  | 2:04 |  | 69 |  | Perfo | 11093 |  | 7:00 |  | 23
Frac- 11 |  |  | Date | 2015-11-11 |  |  | Frac- 12 |  |  | Date | 2015-11-11
VSI Dataset |  | 3H_S11F | RLDF File |  | 3H_S11F |  | VSI Dataset |  | 3H_S12F | RLDF File |  | 3H_S12F
Start Recording |  |  | 3:00 |  |  |  | Start Recording |  |  | 7:51
Event Detection Settings |  |  | 1.8/13 |  |  |  | Event Detection Settings |  |  | 2 / 13
Start Pumping |  |  | 3:41 |  |  |  | Start Pumping |  |  | 9:34
Stop Pumping |  |  | 5:22 |  |  |  | Stop Pumping |  |  | 11:49
Stop Recording |  |  | 5:53 |  |  |  | Stop Recording |  |  | 12:19
Total Number of Events |  |  | 1032 |  |  |  | Total Number of Events |  |  | 1273
Perf Stage - 13 |  |  | Date | 2015-11-11 |  |  | Perf Stage - 14 |  |  | Date | 2015-11-11
VSI Dataset |  | 3H_S13P | Time |  | Event No. |  | VSI Dataset |  | 3H_S14P | Time |  | Event No.
Plug | 11070 |  | 13:08 |  | 16 |  | Plug | 10843 |  | 18:11 |  | 32
Perfo | 11046 |  | 13:09 |  | 17 |  | Perfo | 10822 |  | 18:12 |  | 34
Perfo | 11000 |  | 13:10 |  | 18 |  | Perfo | 10774 |  | 18:15 |  | 37
Perfo | 10955 |  | 13:11 |  | 20 |  | Perfo | 10731 |  | 18:17 |  | 42
Perfo | 10909 |  | 13:12 |  | 21 |  | Perfo | 10683 |  | 18:19 |  | 43
Perfo | 10863 |  | 13:13 |  | 23 |  | Perfo | 10639 |  | 18:21 |  | 46
Frac- 13 |  |  | Date | 2015-11-11 |  |  | Frac- 14 |  |  | Date | 2015-11-11
VSI Dataset |  | 3H_S13F | RLDF File |  | 3H_S13F |  | VSI Dataset |  | 3H_S14F | RLDF File |  | 3H_S14F
Start Recording |  |  | 14:51 |  |  |  | Start Recording |  |  | 19:28
Event Detection Settings |  |  | 2.4 / 13 |  |  |  | Event Detection Settings |  |  | 2.4 / 13
Start Pumping |  |  | 15:08 |  |  |  | Start Pumping |  |  | 19:53
Stop Pumping |  |  | 16:47 |  |  |  | Stop Pumping |  |  | 21:43
Stop Recording |  |  | 17:17 |  |  |  | Stop Recording |  |  | 22:13
Total Number of Events |  |  | 627 |  |  |  | Total Number of Events |  |  | 1038
Perf Stage - 15 |  |  | Date | 2015-11-12 |  |  | Perf Stage - 16 |  |  | Date | 2015-11-12
VSI Dataset |  | 3H_S15P | Time |  | Event No. |  | VSI Dataset |  | 3H_S16P2 | Time |  | Event No.
Plug | 10617 |  | 1:23 |  | 32 |  | Plug | 10432 |  | 6:46 |  | 5
Perfo | 10594 |  | 1:25 |  | 33 |  | Perfo | 10408 |  | 6:48 |  | 8
Perfo | 10547 |  | 1:26 |  | 38 |  | Perfo | 10365 |  | 6:49 |  | 11
Perfo | 10503 |  | 1:27 |  | 39 |  | Perfo | 10316 |  | 6:50 |  | 13
Perfo | 10456 |  | 1:29 |  | 40 |  | Perfo | 10278 |  | 6:51 |  | 15
Perfo | [6 empty] | Perfo
Frac- 15 |  |  | Date | 2015-11-12 |  |  | Frac- 16 |  |  | Date | 2015-11-12
VSI Dataset |  | 3H_S15F | RLDF File |  | 3H_S15F |  | VSI Dataset |  | 3H_S16F | RLDF File |  | 3H_S16F
Start Recording |  |  | 2:37 |  |  |  | Start Recording |  |  | 7:39
Event Detection Settings |  |  | 2.4/13 |  |  |  | Event Detection Settings |  |  | 2.4 / 13
Start Pumping |  |  | 2:54 |  |  |  | Start Pumping |  |  | 7:57
Stop Pumping |  |  | 4:57 |  |  |  | Stop Pumping |  |  | 9:31
Stop Recording |  |  | 5:28 |  |  |  | Stop Recording |  |  | 10:01
Total Number of Events |  |  | 1043 |  |  |  | Total Number of Events |  |  | 881
Perf Stage - 17 |  |  | Date | 2015-11-12 |  |  | Perf Stage - 18 |  |  | Date | 2015-11-13
VSI Dataset |  | 3H_S17P/2/3 | Time |  | Event No. |  | VSI Dataset |  | 3H_S18P | Time |  | Event No.
Plug | 10254 |  | 10:55 |  | 64 |  | Plug | 10071 |  | 7:44 |  | 32
Perfo | 10229 |  | 10:57 |  | 66 |  | Perfo | 10048 |  | 7:46 |  | 35
Perfo | 10185 |  | 11:10 |  | 88 |  | Perfo | 10002 |  | 7:47 |  | 38
Perfo | 10139 |  | 19:33 |  | 298 |  | Perfo | 9959 |  | 7:48 |  | 39
Perfo | 10092 |  | 20:15 |  | 311 |  | Perfo | 9912 |  | 7:54 |  | 52
Perfo | [6 empty] | Perfo
Frac- 17 |  |  | Date | 2015-11-12 |  |  | Frac- 18 |  |  | Date | 2015-11-13
VSI Dataset |  | 3H_S17F/3 | RLDF File |  | 3H_S17F |  | VSI Dataset |  | 3H_S18F | RLDF File |  | 3H_S18F
Start Recording |  |  | 21:28 |  |  |  | Start Recording |  |  | 8:42
Event Detection Settings |  |  | 2.4/13 |  |  |  | Event Detection Settings |  |  | 2.4 / 13
Start Pumping |  |  | 21:42 |  |  |  | Start Pumping |  |  | 8:51
Stop Pumping |  |  | 23:34 |  |  |  | Stop Pumping |  |  | 10:20
Stop Recording |  |  | 12:08 |  |  |  | Stop Recording |  |  | 10:50
Total Number of Events | [6 empty] | Total Number of Events |  |  | 1934
Perf Stage - 19 |  |  | Date | 2015-11-13 |  |  | Perf Stage - 20 |  |  | Date | 2015-11-13
VSI Dataset |  | 3H_S19P | Time |  | Event No. |  | VSI Dataset |  | 3H_S20P2/3 | Time |  | Event No.
Plug | 9891 |  | 12:17 |  | 25 |  | Plug | 9708 |  | 18:56 |  | 30
Perfo | 9865 |  | 13:21 |  | 64 |  | Perfo | 9685 |  | 22:44 |  | 44
Perfo | 9823 |  | 13:23 |  | 66 |  | Perfo | 9639 |  | 22:47 |  | 46
Perfo | 9779 |  | 13:24 |  | 69 |  | Perfo | 9594 |  | 22:53 |  | 49
Perfo | 9732 |  | 13:25 |  | 70 |  | Perfo | 9552 |  | 22:55 |  | 50
Perfo | [6 empty] | Perfo | 9504 |  | 22:57 |  | 51
Frac- 19 |  |  | Date | 2015-11-13 |  |  | Frac- 20 |  |  | Date | 2015-11-13
VSI Dataset |  | 3H_S19F | RLDF File |  | 3H_S19F |  | VSI Dataset |  | 3H_S20F | RLDF File |  | 3H_S20F
Start Recording |  |  | 14:28 |  |  |  | Start Recording |  |  | 23:48
Event Detection Settings |  |  | 2.4 / 13 |  |  |  | Event Detection Settings |  |  | 2.4 / 15
Start Pumping |  |  | 15:13 |  |  |  | Start Pumping |  |  | 23:56
Stop Pumping |  |  | 16:53 |  |  |  | Stop Pumping |  |  | 1:33
Stop Recording |  |  | 17:13 |  |  |  | Stop Recording |  |  | 2:03
Total Number of Events |  |  | 1692 |  |  |  | Total Number of Events |  |  | 1333
Perf Stage - 21 |  |  | Date | 2015-11-14 |  |  | Perf Stage - 22 |  |  | Date | 2015-11-14
VSI Dataset |  | 3H_S21P | Time |  | Event No. |  | VSI Dataset |  | 3H_S22P | Time |  | Event No.
Plug | 9474 |  | 3:00 |  | 53 |  | Plug | 9249 |  | 7:58 |  | 12
Perfo | 9445 |  | 3:02 |  | 57 |  | Perfo | 9227 |  | 7:59 |  | 13
Perfo | 9410 |  | 3:07 |  | 60 |  | Perfo | 9183 |  | 8:00 |  | 16
Perfo | 9365 |  | 3:10 |  | 64 |  | Perfo | 9136 |  | 8:01 |  | 17
Perfo | 9318 |  | 3:12 |  | 72 |  | Perfo | 9087 |  | 8:03 |  | 18
Perfo | 9271 |  | 3:20 |  | 86 |  | Perfo | 9051 |  | 8:04 |  | 19
Frac- 21 |  |  | Date | 2015-11-14 |  |  | Frac- 22 |  |  | Date | 2015-11-14
VSI Dataset |  | 3H_S21F | RLDF File |  | 3H_S21F |  | VSI Dataset |  | 3H_S22F/2/3 | RLDF File |  | 3H_S22F/2/3
Start Recording |  |  | 4:09 |  |  |  | Start Recording |  |  | 9:06
Event Detection Settings |  |  | 2.4 / 15 |  |  |  | Event Detection Settings |  |  | 2.4 / 15
Start Pumping |  |  | 4:55 |  |  |  | Start Pumping |  |  | 9:07
Stop Pumping |  |  | 6:46 |  |  |  | Stop Pumping |  |  | 15:54
Stop Recording |  |  | 7:16 |  |  |  | Stop Recording |  |  | 16:24
Total Number of Events |  |  | 526 |  |  |  | Total Number of Events |  |  | 523
Perf Stage - 23 |  |  | Date | 2015-11-14 |  |  | Perf Stage - 24 |  |  | Date | 2015-11-14
VSI Dataset |  | 3H_S23P | Time |  | Event No. |  | VSI Dataset |  | 3H_S24P | Time |  | Event No.
Plug | 9028 |  | 17:13 |  | 16 |  | Plug | 8789 |  | 22:31 |  | 32
Perfo | 9005 |  | 17:14 |  | 17 |  | Perfo | 8763 |  | 22:32 |  | 35
Perfo | 8959 |  | 17:15 |  | 19 |  | Perfo | 8724 |  | 22:34 |  | 36
Perfo | 8910 |  | 17:16 |  | 20 |  | Perfo | 8678 |  | 22:35 |  | 37
Perfo | 8863 |  | 17:17 |  | 21 |  | Perfo | 8634 |  | 22:38 |  | 41
Perfo | 8814 |  | 17:18 |  | 23 |  | Perfo | 8587 |  | 22:39 |  | 43
Frac- 23 |  |  | Date | 2015-11-14 |  |  | Frac- 24 |  |  | Date | 2015-11-14
VSI Dataset |  | 3H_S23F | RLDF File |  | 3H_S23F |  | VSI Dataset |  | 3H_S24F | RLDF File |  | 3H_S24F
Start Recording |  |  | 18:37 |  |  |  | Start Recording |  |  | 23:21
Event Detection Settings |  |  | 2 / 13 |  |  |  | Event Detection Settings |  |  | 2 / 13
Start Pumping |  |  | 19:23 |  |  |  | Start Pumping |  |  | 23:33
Stop Pumping |  |  | 21:09 |  |  |  | Stop Pumping |  |  | 1:14
Stop Recording |  |  | 21:42 |  |  |  | Stop Recording |  |  | 1:44
Total Number of Events |  |  | 945 |  |  |  | Total Number of Events |  |  | 276
Perf Stage - 25 |  |  | Date | 2015-11-15 |  |  | Perf Stage - 26 |  |  | Date | 2015-11-15
VSI Dataset |  | 3H_S25P | Time |  | Event No. |  | VSI Dataset |  | 3H_S26P | Time |  | Event No.
Plug | 8564 |  | 2:31 |  | 26 |  | Plug | 8333 |  | 6:54 |  | 12
Perfo | 8541 |  | 2:34 |  | 29 |  | Perfo | 8310 |  | 6:55 |  | 16
Perfo | 8495 |  | 2:36 |  | 30 |  | Perfo | 8264 |  | 6:56 |  | 18
Perfo | 8448 |  | 2:42 |  | 32 |  | Perfo | 8220 |  | 6:58 |  | 19
Perfo | 8400 |  | 2:44 |  | 33 |  | Perfo | 8175 |  | 6:59 |  | 21
Perfo | 8356 |  | 2:47 |  | 36 |  | Perfo | 8128 |  | 7:00 |  | 22
Frac- 25 |  |  | Date | 2015-11-15 |  |  | Frac- 26 |  |  | Date | 2015-11-15
VSI Dataset |  | 3H_S25F2 | RLDF File |  | 3H_S25F2 |  | VSI Dataset |  | 3H_S26F | RLDF File |  | 3H_S26F
Start Recording |  |  | 3:42 |  |  |  | Start Recording |  |  | 7:42
Event Detection Settings |  |  | 1.8 / 13 |  |  |  | Event Detection Settings |  |  | 1.8 / 13
Start Pumping |  |  | 3:58 |  |  |  | Start Pumping |  |  | 8:14
Stop Pumping |  |  | 5:39 |  |  |  | Stop Pumping |  |  | 9:40
Stop Recording |  |  | 6:09 |  |  |  | Stop Recording |  |  | 10:10
Total Number of Events |  |  | 395 |  |  |  | Total Number of Events |  |  | 290
Perf Stage - 27 |  |  | Date | 2015-11-15 |  |  | Perf Stage - 28 |  |  | Date | 2015-11-15
VSI Dataset |  | 3H_S27P | Time |  | Event No. |  | VSI Dataset |  | 3H_S28P | Time |  | Event No.
Plug | 8107 |  | 11:07 |  | 14 |  | Plug | 7923 |  | 15:52 |  | 10
Perfo | 8085 |  | 11:08 |  | 15 |  | Perfo | 7901 |  | 15:53 |  | 12
Perfo | 8042 |  | 11:10 |  | 17 |  | Perfo | 7852 |  | 15:54 |  | 13
Perfo | 7993 |  | 11:11 |  | 19 |  | Perfo | 7803 |  | 15:55 |  | 14
Perfo | 7944 |  | 11:13 |  | 20 |  | Perfo | 7753 |  | 15:56 |  | 16
Perfo | [6 empty] | Perfo
Frac- 27 |  |  | Date | 2015-11-15 |  |  | Frac- 28 |  |  | Date | 2015-11-15
VSI Dataset |  | 3H_S27F | RLDF File |  | 3H_S27F |  | VSI Dataset |  | 3H_S28F | RLDF File |  | 3H_S28F
Start Recording |  |  | 12:52 |  |  |  | Start Recording |  |  | 16:55
Event Detection Settings |  |  | 1.8 / 13 |  |  |  | Event Detection Settings |  |  | 1.8 / 13
Start Pumping |  |  | 13:15 |  |  |  | Start Pumping |  |  | 17:00
Stop Pumping |  |  | 14:32 |  |  |  | Stop Pumping |  |  | 18:31
Stop Recording |  |  | 15:02 |  |  |  | Stop Recording |  |  | 19:01
Total Number of Events |  |  | 393 |  |  |  | Total Number of Events |  |  | 263

## Timeline
Engineer | M. Dillon |  |  | Company | Northeast Natural Resources LLC |  |  |  | Well |  | MIP 5H and 3H |  |  |  | Date | 2015-10-27 | Day #
S.O.N. | DC33-00006 |  |  | Field | Monongalia |  |  |  | GeoPhysicist |  | A. Johansen | [5 empty] | TRAVEL
Depth | File# | MCM |  | Pump time |  | To | From | Time |  | Total Hr | RH | LT | Op Hours | Bad Shots/Remarks |  |  | RIGUP
TROUBLESHOOT
[14 empty] | TRAVEL |  |  | PERFORATION Stage #
[14 empty] | Leave Base |  |  | STAGE #
[14 empty] | Arrive at wellsite |  |  | RIGDOWN
[8 empty] | 2015-10-27 | [5 empty] | RIGUP |  |  | TOTAL
[8 empty] | 12:00 | [5 empty] | Safety Meeting
[8 empty] | 12:45 | [5 empty] | Started Rigging up.
[8 empty] | 14:15 | [5 empty] | Tools Checks
[8 empty] | 14:25 | [5 empty] | 30 Minute Surface recording
[8 empty] | 15:15 | [5 empty] | Started Running in Hole
[8 empty] | 15:45 | [5 empty] | Correlation log ran. Depth corrected -5ft
[8 empty] | 15:50 | [5 empty] | On Depth log ran.
[8 empty] | 17:00 | [5 empty] | Tools at a depth of 6040-7140ft.
[8 empty] | 17:30 | [5 empty] | Started 30 Minute Recording
[8 empty] | 2015-10-28 | [5 empty] | Day #1
[8 empty] | 5:45 | [5 empty] | Arrived to Treatment Wellsite for Safety Meeting
[8 empty] | 7:00 | [5 empty] | Tools on and Operational.
[8 empty] | 7:48 | [5 empty] | Generator Surged and killed tool power
[8 empty] | 9:00 | [5 empty] | Tools moving down to 6310-7410ft
[8 empty] | 9:31 | [5 empty] | Tools opening and anchoring 6310-7410ft.
[8 empty] | 10:00 | [5 empty] | Tools in Position, Crane laid down. Ready to record.
| 5H_S1-Real | [12 empty] | STAGE # 1
[8 empty] | 10:28 | [5 empty] | Started Recording
[8 empty] | 11:11 | [5 empty] | Started Fraccing
[8 empty] | 12:06 | [5 empty] | Stopped Fraccing
[8 empty] | 12:36 | [5 empty] | Stopped Recording
| 5H_S1_Re-Perf | [12 empty] | PERFORATION Stage # 1 Re-Perf
[8 empty] | 13:27 | [5 empty] | Started Recording
[8 empty] | 14:20 | [5 empty] | See Perf Notes
[8 empty] | 14:30 | [5 empty] | Moved to Back-up Generator
[8 empty] | 14:40 | [5 empty] | Tools Back Online
Always have spare clamps as backup as the screw may become damaged easily for Standoff H135982 (Hose clamp part number B077715)
| 5H_S1F_Redo | [12 empty] | STAGE # 1 Attempt 2
[8 empty] | 15:34 | [5 empty] | Started Recording
[8 empty] | 15:37 | [5 empty] | Started Fraccing
[8 empty] | 15:55 | [5 empty] | GPS not turned on, starting new file
| 5H_S1F_Redo2 | [6 empty] | 15:56 | [5 empty] | Started Recording
[8 empty] | 17:40 | [5 empty] | Stopped Fraccing
[8 empty] | 18:10 | [5 empty] | Stopped Recording
[8 empty] | 2015-10-29 | [5 empty] | Day #2
| 5H_S2P2 | [12 empty] | PERFORATION Stage # 2
[8 empty] | 6:40 | [5 empty] | Started Recording
[8 empty] | 8:42 | [5 empty] | See Perf Notes
| 5H_S2F | [12 empty] | STAGE # 2
[8 empty] | 10:22 | [5 empty] | Started Recording
[8 empty] | 10:27 | [5 empty] | Started Fraccing
[8 empty] | 12:25 | [5 empty] | Stopped Fraccing
[8 empty] | 12:55 | [5 empty] | Stopped Recording
| 5H_S3P | [12 empty] | PERFORATION Stage # 3
Started Recording
[8 empty] | 13:48 | [5 empty] | See Perf Notes
| 5H_S3F | [12 empty] | STAGE # 3
[8 empty] | 15:08 | [5 empty] | Started Recording
[8 empty] | 15:09 | [5 empty] | Started Fraccing
[8 empty] | 16:44 | [5 empty] | Stopped Fraccing
[8 empty] | 17:14 | [5 empty] | Stopped Recording
| 5H_s4P | [12 empty] | PERFORATION Stage # 4
[8 empty] | 17:57 | [5 empty] | Started Recording
See Perf Notes
| 5H_S4F | [12 empty] | STAGE # 4
[8 empty] | 20:03 | [5 empty] | Started Recording
[8 empty] | 20:07 | [5 empty] | Started Fraccing
[8 empty] | 20:29 | [5 empty] | Ball Seated
[8 empty] | 21:37 | [5 empty] | Stopped Fraccing
[8 empty] | 22:28 | [5 empty] | Stopped Recording
[8 empty] | 2015-10-30 | [5 empty] | Day #3
| 5H_S4F_2 | [12 empty] | STAGE # 4 Injection Test/Try to flush
[8 empty] | 0:21 | [5 empty] | Started Recording
[8 empty] | 0:25 | [5 empty] | Start Pumping
[8 empty] | 0:37 | [5 empty] | Stop Pumping
[8 empty] | 0:59 | [5 empty] | Stop Recording
| 5H_S5P | [12 empty] | PERFORATION Stage # 5
[8 empty] | 2:01 | [5 empty] | Started Recording
See Perf Notes
STAGE # 5
| 5H_S5F | [6 empty] | 4:05 | [5 empty] | Started Recording
[8 empty] | 4:30 | [5 empty] | Start Pumping
[8 empty] | 4:49 | [5 empty] | Ball Seated
[8 empty] | 6:18 | [5 empty] | Stop Pumping
[8 empty] | 6:48 | [5 empty] | Stop Recording
| 5H_S6P | [12 empty] | PERFORATION Stage # 6
[8 empty] | 7:12 | [5 empty] | Started Recording
See Perf Notes
| 5H_S6F | [12 empty] | STAGE # 6
[8 empty] | 12:23 | [5 empty] | Started Recording
[8 empty] | 12:25 | [5 empty] | Start Pumping
[8 empty] | 14:20 | [5 empty] | Stop Pumping
[8 empty] | 14:50 | [5 empty] | Stop Recording
| 5H_S7P | [12 empty] | PERFORATION Stage # 7
[8 empty] | 15:19 | [5 empty] | Started Recording
[8 empty] | 15:40 | [5 empty] | See Perf Notes
| 5H_S7F | [12 empty] | STAGE # 7
[8 empty] | 17:05 | [5 empty] | Started Recording
[8 empty] | 17:14 | [5 empty] | Start Pumping
[8 empty] | 17:49 | [5 empty] | Stopped Pumping
[8 empty] | 18:21 | [5 empty] | Started pumping
[8 empty] | 19:51 | [5 empty] | Stop pumping
[8 empty] | 20:21 | [5 empty] | Stop Recording
| 5H_S8P2 | [12 empty] | PERFORATION Stage # 8
[8 empty] | 21:07 | [5 empty] | Started Recording
See Perf Notes
| 5H_S8F2 | [12 empty] | STAGE # 8
[8 empty] | 22:39 | [5 empty] | Started Recording
[8 empty] | 2015-10-31 | [5 empty] | Day #4
[8 empty] | 2:29 | [5 empty] | Start Pumping
[8 empty] | 4:21 | [5 empty] | Stop Pumping
[8 empty] | 4:51 | [5 empty] | Stop Recording
| 5H_S9P | [12 empty] | PERFORATION Stage # 9
[8 empty] | 5:31 | [5 empty] | Started Recording
See Perf Notes
STAGE # 9
| 5H_S9F | [6 empty] | 8:02 | [5 empty] | Started Recording
[8 empty] | 8:04 | [5 empty] | Start Pumping
[8 empty] | 9:58 | [5 empty] | Stop Pumping
[8 empty] | 10:28 | [5 empty] | Stop Recording
| 5H_S10P | [12 empty] | PERFORATION Stage # 10
[8 empty] | 11:00 | [5 empty] | Started Recording
[8 empty] | 11:17 | [5 empty] | See Perf Notes
| 5H_S10F | [12 empty] | STAGE # 10
[8 empty] | 12:20 | [5 empty] | Started Recording
[8 empty] | 12:25 | [5 empty] | Start Pumping
[8 empty] | 14:13 | [5 empty] | Stop Pumping
[8 empty] | 14:43 | [5 empty] | Stop Recording
| 5H_S11P | [12 empty] | PERFORATION Stage # 11
[8 empty] | 15:13 | [5 empty] | Started Recording
See Perf Notes
| 5H_S11F | [12 empty] | STAGE # 11
[8 empty] | 18:23 | [5 empty] | Started Recording
[8 empty] | 18:58 | [5 empty] | Start Pumping
[8 empty] | 20:45 | [5 empty] | Stop Pumping
[8 empty] | 21:22 | [5 empty] | Stop Recording
| 5H_S12P | [12 empty] | PERFORATION Stage # 12
[8 empty] | 21:46 | [5 empty] | Started Recording
See Perf Notes
| 5H_S12F | [12 empty] | STAGE # 12
[8 empty] | 23:25 | [5 empty] | Started Recording
[8 empty] | 23:28 | [5 empty] | Start Pumping
[8 empty] | 2015-11-01 | [5 empty] | Day #5
[8 empty] | 1:21 | [5 empty] | Stop Pumping
[8 empty] | 1:55 | [5 empty] | Stop Recording
[8 empty] | 2:00 | [5 empty] | Daylight savings, fall back 1 hout
| 5H_S13P | [12 empty] | PERFORATION Stage # 13
[8 empty] | 3:23 | [5 empty] | Started Recording
See Perf Notes
| 5H_S13F | [12 empty] | STAGE # 13
[8 empty] | 4:54 | [5 empty] | Started Recording
[8 empty] | 5:13 | [5 empty] | Start Pumping
[8 empty] | 5:56 | [5 empty] | Stopped Pumping
[8 empty] | 6:49 | [5 empty] | Start Pumping
[8 empty] | 8:12 | [5 empty] | Stop Pumping
[8 empty] | 8:42 | [5 empty] | Stop Recording
| 5H_S14P | [12 empty] | PERFORATION Stage # 14
[8 empty] | 9:26 | [5 empty] | Started Recording
[8 empty] | 9:40 | [5 empty] | See Perf Notes
| 5H_S14F | [12 empty] | STAGE # 14
[8 empty] | 10:39 | [5 empty] | Started Recording
[8 empty] | 10:45 | [5 empty] | Start Pumping
[8 empty] | 12:31 | [5 empty] | Stop Pumping
[8 empty] | 13:01 | [5 empty] | Stop Recording
| 5H_S15P | [12 empty] | PERFORATION Stage # 15
[8 empty] | 13:39 | [5 empty] | Started Recording
[8 empty] | 13:41 | [5 empty] | See Perf Notes
| 5H_S15F | [12 empty] | STAGE # 15
[8 empty] | 15:02 | [5 empty] | Started Recording
[8 empty] | 15:15 | [5 empty] | Start Pumping
[8 empty] | 16:00 | [5 empty] | Shuttles 11 and 12 are Red on SNM
[8 empty] | 16:12 | [5 empty] | Now just shuttle 12, will change network after stage
[8 empty] | 17:00 | [5 empty] | Stop Pumping
[8 empty] | 17:02 | [5 empty] | Stop Recording
[8 empty] | 17:04 | [5 empty] | Restarting Computer
| 5H_S16P | [12 empty] | PERFORATION Stage # 16
[8 empty] | 17:10 | [5 empty] | Started Recording
See Perf Notes
| 5H_S16F | [12 empty] | STAGE # 16
[8 empty] | 19:11 | [5 empty] | Started Recording
[8 empty] | 21:55 | [5 empty] | Start Pumping
[8 empty] | 23:38 | [5 empty] | Stop Pumping
[8 empty] | 2015-11-02 | [5 empty] | Day #6
[8 empty] | 0:08 | [5 empty] | Stop Recording
| 5H_S17P | [12 empty] | PERFORATION Stage # 17
[8 empty] | 0:38 | [5 empty] | Started Recording
[8 empty] | 2:14 | [5 empty] | See Perf Notes
| 5H_S17F | [12 empty] | STAGE # 17
[8 empty] | 2:14 | [5 empty] | Started Recording
[8 empty] | 2:42 | [5 empty] | Start Pumping
[8 empty] | 4:43 | [5 empty] | Stop Pumping
[8 empty] | 5:13 | [5 empty] | Stop Recording
| 5H_S18P | [12 empty] | PERFORATION Stage # 18
[8 empty] | 5:41 | [5 empty] | Started Recording
See Perf Notes
[8 empty] | 6:00 | [5 empty] | Standing by on Location until they rebuild the pad as it
collapsed under the weight of the forklift
[8 empty] | 18:00 | [5 empty] | Still standing by.
[8 empty] | 2015-11-03 | [5 empty] | Day #7
| 5H_S18F | [12 empty] | STAGE # 18
[8 empty] | 0:15 | [5 empty] | Started Recording
[8 empty] | 0:47 | [5 empty] | Start Pumping
[8 empty] | 2:52 | [5 empty] | Stop Pumping
[8 empty] | 3:32 | [5 empty] | Stop Recording
| 5H_S19P | [12 empty] | PERFORATION Stage # 19
[8 empty] | 3:58 | [5 empty] | Started Recording
See Perf Notes
[8 empty] | 4:17 | [5 empty] | Lost Wafe connection, missed first shot, asked wireline to wait to
reboot WAFE and computer
[8 empty] | 4:26 | [5 empty] | Everything got back to working, recorded shot2-shot5
| 5H_S19F | [12 empty] | STAGE # 19
[8 empty] | 6:47 | [5 empty] | Started Recording
[8 empty] | 8:00 | [5 empty] | Start Pumping
[8 empty] | 8:32 | [5 empty] | Upped the Threshold to 2
[8 empty] | 9:31 | [5 empty] | Upped Threshold to 2.2
[8 empty] | 9:43 | [5 empty] | Stop Pumping
[8 empty] | 10:13 | [5 empty] | Stop Recording
| 5H_S20P | [12 empty] | PERFORATION Stage # 20
[8 empty] | 10:30 | [5 empty] | Started Recording
[8 empty] | 10:48 | [5 empty] | See Perf Notes
[8 empty] | 11:22 | [5 empty] | Lost Wafe connection
| 5H_S20F | [12 empty] | STAGE # 20
[8 empty] | 11:51 | [5 empty] | Started Recording
[8 empty] | 11:53 | [5 empty] | Start Pumping
[8 empty] | 13:32 | [5 empty] | Stop Pumping
[8 empty] | 14:02 | [5 empty] | Stop Recording
| 5H_S21P | [12 empty] | PERFORATION Stage # 21
[8 empty] | 14:31 | [5 empty] | Started Recording
[8 empty] | 14:49 | [5 empty] | See Perf Notes
| 5H_S21F | [12 empty] | STAGE # 21
[8 empty] | 16:04 | [5 empty] | Started Recording
[8 empty] | 16:16 | [5 empty] | Start Pumping
[8 empty] | 18:00 | [5 empty] | Stop Pumping
[8 empty] | 18:35 | [5 empty] | Stop Recording
| 5H_S22P | [12 empty] | PERFORATION Stage # 22
[8 empty] | 18:52 | [5 empty] | Started Recording
See Perf Notes
| 5H_S22F | [12 empty] | STAGE # 22
[8 empty] | 19:40 | [5 empty] | Started Recording
[8 empty] | 20:06 | [5 empty] | Start Pumping
[8 empty] | 21:14 | [5 empty] | Shuttles 11 and 12 are Red on SNM
[8 empty] | 21:20 | [5 empty] | Now just shuttle 12, will change network after stage
[8 empty] | 21:43 | [5 empty] | Stop Pumping
[8 empty] | 22:13 | [5 empty] | Stop Recording
[8 empty] | 22:14 | [5 empty] | Restarting Computer
| 5H_S23P | [12 empty] | PERFORATION Stage # 23
[8 empty] | 22:37 | [5 empty] | Started Recording
See Perf Notes
| 5H_S23F | [12 empty] | STAGE # 23
[8 empty] | 23:37 | [5 empty] | Started Recording
[8 empty] | 2015-11-04 | [5 empty] | Day #8
[8 empty] | 1:42 | [5 empty] | Stop Pumping
[8 empty] | 2:12 | [5 empty] | Stop Recording
| 5H_S24P | [12 empty] | PERFORATION Stage # 24
[8 empty] | 2:36 | [5 empty] | Started Recording
See Perf Notes
| 5H_S24F | [12 empty] | STAGE # 24
[8 empty] | 3:31 | [5 empty] | Started Recording
[8 empty] | 3:49 | [5 empty] | Shuttle 12 turned red in SNM, will change network after stage
| 5H_S24F_2 | [6 empty] | 3:56 | [5 empty] | Restart computer, change networking since still waiting for frack
[8 empty] | 4:03 | [5 empty] | Started Recording
[8 empty] | 6:10 | [5 empty] | Stopped recording - Leak on Lines
| 5H_S23F3 | [6 empty] | 6:44 | [5 empty] | Started Recording
[8 empty] | 6:53 | [5 empty] | Start Pumping
[8 empty] | 8:27 | [5 empty] | Stop Pumping
[8 empty] | 8:57 | [5 empty] | Stop Recording
| 5H_S25P | [12 empty] | PERFORATION Stage # 25
[8 empty] | 9:19 | [5 empty] | Started Recording
[8 empty] | 9:31 | [5 empty] | See Perf Notes
| 5H_S25F | [12 empty] | STAGE # 25
[8 empty] | 10:24 | [5 empty] | Started Recording
[8 empty] | 10:26 | [5 empty] | Start Pumping
[8 empty] | 12:02 | [5 empty] | Stop Pumping
[8 empty] | 12:32 | [5 empty] | Stop Recording
| 5H_S26P | [12 empty] | PERFORATION Stage # 26
[8 empty] | 13:01 | [5 empty] | Started Recording
[8 empty] | 13:05 | [5 empty] | See Perf Notes
| 5H_S26F | [12 empty] | STAGE # 26
[8 empty] | 14:07 | [5 empty] | Started Recording
[8 empty] | 14:08 | [5 empty] | Start Pumping
[8 empty] | 14:28 | [5 empty] | Lost GPS Signal.
[8 empty] | 14:35 | [5 empty] | Reestablished GPS
[8 empty] | 15:48 | [5 empty] | Stop Pumping
[8 empty] | 16:18 | [5 empty] | Stop Recording
| 5H_S27P | [12 empty] | PERFORATION Stage # 27
[8 empty] | 16:43 | [5 empty] | Started Recording
[8 empty] | 16:56 | [5 empty] | See Perf Notes
| 5H_S27F | [12 empty] | STAGE # 27
[8 empty] | 18:32 | [5 empty] | Started Recording
[8 empty] | 20:42 | [5 empty] | Start Pumping
[8 empty] | 22:40 | [5 empty] | Stop Pumping
[8 empty] | 23:13 | [5 empty] | Stop Recording
| 5H_S28P | [12 empty] | PERFORATION Stage # 28
[8 empty] | 23:45 | [5 empty] | Started Recording
[8 empty] | 2015-11-05 | [5 empty] | Day #9
See Perf Notes
| 5H_S28F | [12 empty] | STAGE # 28
[8 empty] | 1:28 | [5 empty] | Started Recording
[8 empty] | 1:41 | [5 empty] | Start Pumping
[8 empty] | 3:17 | [5 empty] | Stop Pumping
[8 empty] | 3:55 | [5 empty] | Stop Recording
| 5H_S29P | [12 empty] | PERFORATION Stage # 29
[8 empty] | 5:03 | [5 empty] | Started Recording
[8 empty] | 5:18 | [5 empty] | See Perf Notes
| 5H_S29F | [12 empty] | STAGE # 29
[8 empty] | 6:29 | [5 empty] | Started Recording
[8 empty] | 6:55 | [5 empty] | Start Pumping
[8 empty] | 8:34 | [5 empty] | Stop Pumping
[8 empty] | 9:04 | [5 empty] | Stop Recording
| 5H_S30P | [12 empty] | PERFORATION Stage # 30
[8 empty] | 9:31 | [5 empty] | Started Recording
[8 empty] | 9:34 | [5 empty] | See Perf Notes
| 5H_S30F | [12 empty] | STAGE # 30
[8 empty] | 10:38 | [5 empty] | Started Recording
[8 empty] | 11:33 | [5 empty] | Start Pumping
[8 empty] | 13:05 | [5 empty] | Stop Pumping
[8 empty] | 13:35 | [5 empty] | Stop Recording
[8 empty] | 13:35 | [5 empty] | Moving iron to the 3H
[8 empty] | 17:00 | [5 empty] | Put on standby until Saturday Morning
[8 empty] | 2015-11-08 | [5 empty] | Day #12
| 3H_S7P | [12 empty] | PERFORATION Stage # 7
[8 empty] | 22:40 | [5 empty] | Started Recording
See Perf Notes
[8 empty] | 2015-11-09 | [5 empty] | Day #13
| 3H_S7F | [12 empty] | STAGE # 7
[8 empty] | 0:47 | [5 empty] | Started Recording
[8 empty] | 1:27 | [5 empty] | Start Pumping
[8 empty] | 3:32 | [5 empty] | Stop Pumping
[8 empty] | 4:06 | [5 empty] | Stop Recording
| 3H_S8P | [12 empty] | PERFORATION Stage # 8
[8 empty] | 4:28 | [5 empty] | Started Recording
See Perf Notes
STAGE # 8
| 3H_S8F | [6 empty] | 6:44 | [5 empty] | Started Recording
[8 empty] | 8:14 | [5 empty] | Start Pumping
[8 empty] | 10:06 | [5 empty] | Stop Pumping
[8 empty] | 10:36 | [5 empty] | Stop Recording
| 3H_S9P | [12 empty] | PERFORATION Stage # 9
[8 empty] | 11:47 | [5 empty] | Started Recording
See Perf Notes
| 3H_S9F | [12 empty] | STAGE # 9
[8 empty] | 13:51 | [5 empty] | Started Recording
[8 empty] | 14:07 | [5 empty] | Bumped threshold to 2 from 1.8
[8 empty] | 15:49 | [5 empty] | Start Pumping
[8 empty] | 17:39 | [5 empty] | Stop Pumping
[8 empty] | 18:09 | [5 empty] | Stop Recording
| 3H_S10P | [12 empty] | PERFORATION Stage # 10
[8 empty] | 18:57 | [5 empty] | Started Recording
See Perf Notes
| 3H_S10F | [12 empty] | STAGE # 10
[8 empty] | 20:34 | [5 empty] | Started Recording
[8 empty] | 20:58 | [5 empty] | Start Pumping
[8 empty] | 22:39 | [5 empty] | Stop Pumping
[8 empty] | 23:15 | [5 empty] | Stop Recording
[8 empty] | 2015-11-10 | [5 empty] | Day #14
| 3H_S11P | [12 empty] | PERFORATION Stage # 11
[8 empty] | 0:15 | [5 empty] | Pumped Port plug off the guns. They are flowing back
[8 empty] | 2015-11-11 | [5 empty] | Day #15
[8 empty] | 1:23 | [5 empty] | Started Recording
See Perf Notes
| 3H_S11F | [12 empty] | STAGE # 11
[8 empty] | 3:00 | [5 empty] | Started Recording
[8 empty] | 3:41 | [5 empty] | Start Pumping
[8 empty] | 5:22 | [5 empty] | Stop Pumping
[8 empty] | 5:53 | [5 empty] | Stop Recording
| 3H_S12P | [12 empty] | PERFORATION Stage # 12
[8 empty] | 6:36 | [5 empty] | Started Recording
[8 empty] | 6:54 | [5 empty] | See Perf Notes
| 3H_S12F | [12 empty] | STAGE # 12
[8 empty] | 7:51 | [5 empty] | Started Recording
[8 empty] | 9:34 | [5 empty] | Start Pumping
[8 empty] | 10:40 | [5 empty] | Bumped threshold to 2.2 from 2
[8 empty] | 11:49 | [5 empty] | Stop Pumping
[8 empty] | 12:19 | [5 empty] | Stop Recording
| 3H_S13P | [12 empty] | PERFORATION Stage # 13
[8 empty] | 13:00 | [5 empty] | Started Recording
[8 empty] | 13:07 | [5 empty] | See Perf Notes
| 3H_S13F | [12 empty] | STAGE # 13
[8 empty] | 14:51 | [5 empty] | Started Recording
[8 empty] | 15:08 | [5 empty] | Start Pumping
[8 empty] | 16:47 | [5 empty] | Stop Pumping
[8 empty] | 17:17 | [5 empty] | Stop Recording
| 3H_S14P | [12 empty] | PERFORATION Stage # 14
[8 empty] | 18:00 | [5 empty] | Started Recording
[8 empty] | 18:10 | [5 empty] | See Perf Notes
| 3H_S14F | [12 empty] | STAGE # 14
[8 empty] | 19:28 | [5 empty] | Started Recording
[8 empty] | 19:53 | [5 empty] | Start Pumping
[8 empty] | 20:11 | [5 empty] | Increased rate
[8 empty] | 21:43 | [5 empty] | Stop Pumping
[8 empty] | 22:13 | [5 empty] | Stop Recording
[8 empty] | 2015-11-12 | [5 empty] | Day #16
| 3H_S15P | [12 empty] | PERFORATION Stage # 15
[8 empty] | 0:55 | [5 empty] | Started Recording
[8 empty] | 1:23 | [5 empty] | See Perf Notes
| 3H_S15F | [12 empty] | STAGE # 15
[8 empty] | 2:37 | [5 empty] | Started Recording
[8 empty] | 2:54 | [5 empty] | Start Pumping
[8 empty] | 4:57 | [5 empty] | Stop Pumping
[8 empty] | 5:28 | [5 empty] | Stop Recording
| 3H_S16P | [12 empty] | PERFORATION Stage # 16
[8 empty] | 6:45 | [5 empty] | Started Recording
[8 empty] | 6:48 | [5 empty] | See Perf Notes
| 3H_S16F | [12 empty] | STAGE # 16
[8 empty] | 7:39 | [5 empty] | Started Recording
[8 empty] | 7:57 | [5 empty] | Start Pumping
[8 empty] | 9:31 | [5 empty] | Stop Pumping
[8 empty] | 10:01 | [5 empty] | Stop Recording
| 3H_S17P | [12 empty] | PERFORATION Stage # 17
| 3H_S17P2 | [6 empty] | 10:36 | [5 empty] | Started Recording
[8 empty] | 10:50 | [5 empty] | Did not get final two guns. POOH and checking guns.
[8 empty] | 12:00 | [5 empty] | Making another attempt to get last two guns.
| 3H_S17P3 | [6 empty] | 18:34 | [5 empty] | Started Recording (final two guns)
[8 empty] | 19:32 | [5 empty] | See Perf Notes
| 3H_S17F | [12 empty] | STAGE # 17
[8 empty] | 21:28 | [5 empty] | Started Recording
[8 empty] | 21:42 | [5 empty] | Start Pumping
[8 empty] | 23:34 | [5 empty] | Frac Trucks Stopped Pumping
[8 empty] | 2015-11-13 | [5 empty] | Day #17
[8 empty] | 0:08 | [5 empty] | Lost connection to WAFE
| 3H_S18P | [12 empty] | PERFORATION Stage # 18
[8 empty] | 7:11 | [5 empty] | Started Recording
[8 empty] | 7:44 | [5 empty] | See Perf Notes
| 3H_S18F | [12 empty] | STAGE # 18
[8 empty] | 8:42 | [5 empty] | Started Recording
[8 empty] | 8:51 | [5 empty] | Start Pumping
[8 empty] | 10:20 | [5 empty] | Stop Pumping
[8 empty] | 10:50 | [5 empty] | Stop Recording
| 3H_S19P | [12 empty] | PERFORATION Stage # 19
[8 empty] | 11:59 | [5 empty] | Started Recording
[8 empty] | 12:16 | [5 empty] | See Perf Notes
| 3H_S19F | [12 empty] | STAGE # 19
[8 empty] | 14:28 | [5 empty] | Started Recording
[8 empty] | 15:13 | [5 empty] | Start Pumping
[8 empty] | 16:53 | [5 empty] | Stop Pumping
[8 empty] | 17:23 | [5 empty] | Stop Recording
| 3H_S20P2 | [12 empty] | PERFORATION Stage # 20
[8 empty] | 18:30 | [5 empty] | Started Recording
[8 empty] | 18:56 | [5 empty] | See Perf Notes
[8 empty] | 19:34 | [5 empty] | Pulled out to re-orient guns
| 3H_S20P3 | [6 empty] | 21:38 | [5 empty] | Started Recording
[8 empty] | 22:44 | [5 empty] | See Perf Notes
| 3H_S20F | [12 empty] | STAGE # 20
[8 empty] | 23:48 | [5 empty] | Started Recording
[8 empty] | 23:56 | [5 empty] | Start Pumping
[8 empty] | 2015-11-14 | [5 empty] | Day #18
[8 empty] | 1:27 | [5 empty] | Changed num of traces from 13 to 15
[8 empty] | 1:33 | [5 empty] | Stop Pumping
[8 empty] | 2:03 | [5 empty] | Stop Recording
| 3H_S21P | [12 empty] | PERFORATION Stage # 21
[8 empty] | 2:38 | [5 empty] | Started Recording
[8 empty] | 3:00 | [5 empty] | See Perf Notes
| 3H_S21F | [12 empty] | STAGE # 21
[8 empty] | 4:09 | [5 empty] | Started Recording
[8 empty] | 4:55 | [5 empty] | Start Pumping
[8 empty] | 5:17 | [5 empty] | Performed step down test
[8 empty] | 5:30 | [5 empty] | Resumed pumping
[8 empty] | 6:46 | [5 empty] | Stop Pumping
[8 empty] | 7:16 | [5 empty] | Stop Recording
| 3H_S22P | [12 empty] | PERFORATION Stage # 22
[8 empty] | 7:40 | [5 empty] | Started Recording
[8 empty] | 7:58 | [5 empty] | See Perf Notes
| 3H_S22F | [12 empty] | STAGE # 22
| 3H_S22F2 | [6 empty] | 9:06 | [5 empty] | Started Recording
| 3H_S22F3 | [6 empty] | 9:07 | [5 empty] | Start Pumping
[8 empty] | 9:43 | [5 empty] | Lowered threshold to 2 / 13
[8 empty] | 10:43 | [5 empty] | Stopped Pumping -Surface issues
[8 empty] | 11:00 | [5 empty] | Moved RLDF upload to Temporary Interact folder.
[8 empty] | 11:55 | [5 empty] | Stopped Recording
[8 empty] | 11:55 | [5 empty] | Started Recording
[8 empty] | 12:10 | [5 empty] | Stopped Recording
[8 empty] | 15:11 | [5 empty] | Resumed Recording
[8 empty] | 15:13 | [5 empty] | Resumed Pumping
[8 empty] | 15:54 | [5 empty] | Stop Pumping
[8 empty] | 16:24 | [5 empty] | Stop Recording
| 3H_S23P | [12 empty] | PERFORATION Stage # 23
[8 empty] | 16:54 | [5 empty] | Started Recording
[8 empty] | 17:12 | [5 empty] | See Perf Notes
| 3H_S23F | [12 empty] | STAGE # 23
[8 empty] | 18:37 | [5 empty] | Started Recording
[8 empty] | 19:23 | [5 empty] | Start Pumping
[8 empty] | 21:09 | [5 empty] | Stop Pumping
[8 empty] | 21:42 | [5 empty] | Stop Recording
| 3H_S24P | [12 empty] | PERFORATION Stage # 24
[8 empty] | 22:10 | [5 empty] | Started Recording
[8 empty] | 22:30 | [5 empty] | See Perf Notes
| 3H_S24F | [12 empty] | STAGE # 24
[8 empty] | 23:21 | [5 empty] | Started Recording
[8 empty] | 23:33 | [5 empty] | Start Pumping
[8 empty] | 2015-11-15 | [5 empty] | Day #19
[8 empty] | 1:14 | [5 empty] | Stop Pumping
[8 empty] | 1:44 | [5 empty] | Stop Recording
| 3H_S25P | [12 empty] | PERFORATION Stage # 25
[8 empty] | 2:06 | [5 empty] | Started Recording
[8 empty] | 2:31 | [5 empty] | See Perf Notes
| 3H_S25F2 | [12 empty] | STAGE # 25
[8 empty] | 3:42 | [5 empty] | Started Recording
[8 empty] | 3:58 | [5 empty] | Start Pumping
[8 empty] | 4:37 | [5 empty] | Lowered threshold to 1.8 / 13
[8 empty] | 5:39 | [5 empty] | Stop Pumping
[8 empty] | 6:09 | [5 empty] | Stop Recording
| 3H_S26P | [12 empty] | PERFORATION Stage # 26
[8 empty] | 6:37 | [5 empty] | Started Recording
[8 empty] | 6:54 | [5 empty] | See Perf Notes
| 3H_S26F | [12 empty] | STAGE # 26
[8 empty] | 7:42 | [5 empty] | Started Recording
[8 empty] | 8:14 | [5 empty] | Start Pumping
[8 empty] | 9:40 | [5 empty] | Stop Pumping
[8 empty] | 10:10 | [5 empty] | Stop Recording
| 3H_S27P | [12 empty] | PERFORATION Stage # 27
[8 empty] | 10:41 | [5 empty] | Started Recording
[8 empty] | 11:07 | [5 empty] | See Perf Notes
| 3H_S27F | [12 empty] | STAGE # 27
[8 empty] | 12:52 | [5 empty] | Started Recording
[8 empty] | 13:15 | [5 empty] | Start Pumping
[8 empty] | 14:32 | [5 empty] | Stop Pumping
[8 empty] | 15:02 | [5 empty] | Stop Recording
| 3H_S28P | [12 empty] | PERFORATION Stage # 28
[8 empty] | 15:37 | [5 empty] | Started Recording
[8 empty] | 15:52 | [5 empty] | See Perf Notes
| 3H_S28F | [12 empty] | STAGE # 28
[8 empty] | 16:55 | [5 empty] | Started Recording
[8 empty] | 17:00 | [5 empty] | Start Pumping
[8 empty] | 18:31 | [5 empty] | Stop Pumping
[8 empty] | 19:01 | [5 empty] | Stop Recording
[8 empty] | 2015-11-16 | [5 empty] | Day #20
[8 empty] | 6:30 | [5 empty] | Arrived on Location to rig down.
[8 empty] | 7:00 | [5 empty] | Held Safety Meeting
[8 empty] | 7:30 | [5 empty] | Started Rigging Down
[8 empty] | 10:45 | [5 empty] | Finished Rigging Down

## Job Debrief
USL Seismic
HFM Debrief Cover Sheet
Checklist
[6 empty] | Yes | No | N/A
Rig Up Date | 2015-10-27 12:00 |  | Rig Down Date: | 2015-11-16 12:00 | Logs delivered to client
Company | Northeast Natural Resources LLC |  |  |  | Copy of SO
Tool | VSI | 12 | Survey Type: | HFM | WRS Time Activity Sheet
Monitor Well Name | MIP Science Well |  |  |  | WRS Time and Eqmt counter Entered
Treatment Well | MIP 5H and 3H |  |  |  | LT Notification # and Status (Ritewin)
Field | Monongalia |  |  |  | Predeparture Wellsite Checklist
Seismic Eng | F. Richardson / M. Dillon |  |  |  | Vehicle Inspection Check sheet
Seismic Op(s) | J. Montez |  |  |  | QSHE RIR
Logging Eng | M. Dillon |  |  |  | Copy of any JSA and HARC
SO# | DC33-00006 |  |  |  | Quest Service Quality Notification
District | Bradford |  | Truck #: | 303 | Failure analysis / Fishing report
# Stages | 60 |  |  |  | SQ Issues
Depth | 7140 |  |  |  | CD of the data / uploaded to Transact
Deviation | .1* |  |  |  | Copy of FIT and TRIM History
BHT | 160 |  |  |  | Borrowed tools Trimmed and returned
BHP | 3638.544 |  |  |  | Tools Trimmed, Tagged and Job Ready
Operating Time | 20 |  |  |  | Source Maintenance Done
Lost Time | 0 |  |  |  | Recipts for any hotshots, Hotels, Airfare
Field Processing | Yes | X |  | No | Debrief with Sales Engineer
Field Processor | A. Johansen
Leave Shop | 2015-10-26 10:00
Return Shop | 2015-11-16 12:00
Tools / Services on the Job (Include the serial numbers for sondes cartrides and housings)
Explaination of "No" Answers:
Issues which need to Follow up
Brief Comments concerning Job/ Services