## Obs Log
Engineer | Devin Paulk |  | Company | Northeast Natural Energy |  |  |  | Well |  | MIP-3H |  |  |  |  | Date | 2015-11-05
Depth | File# | Stack # | Bad shots |  | To | From | Time |  | TOFS | Gain | Stage | Cluster # | Bad Shots/Remarks
[7 empty] | 9:00 | [5 empty] | Day 1 (11-05-2015) Arrive on site
[7 empty] | 9:58 | [5 empty] | Setting up docking station
[7 empty] | 10:38 | [5 empty] | Waiting to finish frac on MIP-5h
[7 empty] | 13:45 | [5 empty] | Setting up ASE session for MIP-3H
[7 empty] | 14:00 | [5 empty] | Tour on Site
[7 empty] | 15:00 | [5 empty] | Tour's ended
[7 empty] | 15:41 | [5 empty] | Setting up powerpoint for internal presentation
[7 empty] | 17:30 | [5 empty] | Relieved by Night Crew
[7 empty] | 17:45 | [5 empty] | Safety Meeting
[7 empty] | 19:00 | [5 empty] | Shut down DTS. Waiting to start 3H. Expect start around 1a.m.
[7 empty] | 19:20 | [5 empty] | Prepare Ultra Session NNE_MW3H_TW3H for Injection Test. It is now v.00002
[7 empty] | 19:25 | [5 empty] | Continue waiting to begin MIP-3H
[7 empty] | 22:10 | [5 empty] | Frac crew testing pumps
[7 empty] | 22:25 | [5 empty] | Printed Perf/Frac Program and Perf/Frac Depth Diagram
[7 empty] | 23:45 | [5 empty] | Pressure Testing Wellhead on 3H
Day 2 (11-6-2015)
[7 empty] | 1:10 | [5 empty] | Start DTS and hDVS for Injection Test
[7 empty] | 1:15 | [5 empty] | Waiting on Frac to begin pumping
[7 empty] | 2:01 | [5 empty] | Begin Injection Test
[7 empty] | 2:09 | [5 empty] | Injecting acid
[7 empty] | 2:45 | [5 empty] | Loss of cummunication to Pump 9 reported by Frac
[7 empty] | 2:47 | [5 empty] | Pump 9 back online
[7 empty] | 2:50 | [5 empty] | Stop Pumping. Injection Test Completed
[7 empty] | 2:55 | [5 empty] | Waiting on Wireline to begin running Perf guns for Stage 1
[7 empty] | 2:59 | [5 empty] | Stop DTS Acquisition
[7 empty] | 3:00 | [5 empty] | Prepare DTS Session for Stage 1 Perf. Will be v.00003
[7 empty] | 3:08 | [5 empty] | hDVS Stopped
[7 empty] | 3:47 | [5 empty] | Start DTS and hDVS data
[7 empty] | 3:48 | [5 empty] | Pressure testing Lubricator
[7 empty] | 3:57 | [5 empty] | Wireline running perf guns
[7 empty] | 4:04 | [5 empty] | hDVS recording paused until guns reach the heel and Frac crew begins pumping
[7 empty] | 4:36 | [5 empty] | Resume hDVS data Acquisition
[7 empty] | 5:17 | [5 empty] | Begin Pump down
[7 empty] | 6:00 | [5 empty] | Safety Meeting and day crew on site
[7 empty] | 8:01 | [5 empty] | Restart WellSync due to memory loss
[7 empty] | 8:17 | [5 empty] | Leak on well side of frac equipment shutting down, stopping ASE to adjust asset
[7 empty] | 8:28 | [5 empty] | Preparing to run acid at 20 B/M
[7 empty] | 8:48 | [5 empty] | Leak in valve on pump, fixing leak
[7 empty] | 8:55 | [5 empty] | pressure testing pumps
[7 empty] | 9:00 | [5 empty] | finished testing pumps
[7 empty] | 9:04 | [5 empty] | pumping fluid and acid at 12.7 b/m
[7 empty] | 9:04 | [5 empty] | HDVS started recording
[7 empty] | 9:34 | [5 empty] | Finished pumping acid, shutting in well and getting ready for wireline
[7 empty] | 9:46 | [5 empty] | Stopping HDVS
[7 empty] | 9:53 | [5 empty] | Wireline preparing to run guns
[7 empty] | 10:00 | [5 empty] | Leak at another check valve
[7 empty] | 10:24 |  |  |  | 1 |  | wireline guns RIH
[7 empty] | 10:59 |  |  |  | 1 |  | Begin pump down guns at 9.5 b/m
[7 empty] | 11:03 |  |  |  | 1 |  | pumping at 12 b/m
[7 empty] | 11:07 |  |  |  | 1 |  | pumping at 14 b/m, Wellsync restarted due to memory loss
[7 empty] | 11:24 |  |  |  | 1 |  | pumping 15.9 b/m ,Start recording HDVS
[7 empty] | 11:36 |  |  |  | 1 |  | increased pump rate to 17 b/m
[7 empty] | 12:01 |  |  |  | 1 |  | stopped pumping
[7 empty] | 12:09 |  |  |  | 1 |  | starting pumps at 2 b/m and increasing to 4 b/m
[7 empty] | 12:10 |  |  |  | 1 |  | Increased pump rate to 14 b/m
[7 empty] | 12:11 |  |  |  | 1 |  | Increased pump rate to 18 b/m
[7 empty] | 12:30 |  |  |  | 1 |  | Guns stopped moving
[7 empty] | 12:31 |  |  |  | 1 |  | stopped pumping
[7 empty] | 12:45 |  |  |  | 1 |  | Started pumping 14 b/m
[7 empty] | 12:47 |  |  |  | 1 |  | increasing to 16 b/m
[7 empty] | 12:48 |  |  |  | 1 |  | Increasing to 18 b/m
[7 empty] | 13:01 |  |  |  | 1 |  | Stop pumping
[7 empty] | 13:09 |  |  |  | 1 |  | New HDVS session started
[7 empty] | 13:41 |  |  |  | 1 |  |  | Pumping 17 b/m
[7 empty] | 14:16 |  |  |  | 1 |  |  | Pumping
[7 empty] | 14:17 |  |  |  | 1 |  | Increase rate to 16 b/m
[7 empty] | 14:27 |  |  |  | 1 |  | Pump off
[7 empty] | 14:39 |  |  |  | 1 | 1 | Shooting stage 1 BP #3
[7 empty] | 14:43 |  |  |  | 1 | 2 | Shooting Stage 1 BP #4
[7 empty] | 14:48 |  |  |  | 1 |  | pumping to change gun orientation
[7 empty] | 14:52 |  |  |  | 1 | 3 | Shooting Stage 1 BP#5
[7 empty] | 14:55 |  |  |  | 1 | 4 | Shooting Stage 1 BP#6
[7 empty] | 14:59 | [5 empty] | Pulling guns out of hole
[7 empty] | 16:07 | [5 empty] | Wireline out of well
[7 empty] | 16:40 | [5 empty] | Started Pumping, 16 b/m
[7 empty] | 16:45 | [5 empty] | increaseing to 24 b/m
[7 empty] | 16:50 | [5 empty] | increasing to 42 b/m
[7 empty] | 16:56 | [5 empty] | increasing to 60 b/m
[7 empty] | 17:00 | [5 empty] | at 70 b/m
[7 empty] | 17:03 | [5 empty] | at 81 b/m
[7 empty] | 17:19 | [5 empty] | pump #6 stopped working
[7 empty] | 17:22 | [5 empty] | at 90.57 b/m
[7 empty] | 17:42 | [5 empty] | Switched to higher propent
[7 empty] | 19:05 | [5 empty] | Finish Frac on Stage 1
[7 empty] | 19:43 | [5 empty] | Change Ultra session for Stage 2 Perf (v.00005)
[7 empty] | 20:20 |  |  |  | 2 |  | Running in Guns for Stage 2 Perf
[7 empty] | 21:01 |  |  |  | 2 |  | Start Pump Down of Perf Guns AT 16 bpm
[7 empty] | 21:39 |  |  |  | 2 |  | Stop Pump Down. Will pull up and go back down to reorient WPP.
[7 empty] | 21:48 |  |  |  | 2 |  | Pull up complete, begin Pump Down again at 13.80 bpm
[7 empty] | 21:50 |  |  |  | 2 |  | Stop Pump down again. Begin recording hDVS
[7 empty] | 21:59 |  |  |  | 2 |  | WL WPP tool not oriented properly. Will attemp to pump between 3 and 14 bpm to rotate.
[7 empty] | 23:10 |  |  |  | 2 | 1 | Shooting Stage 2 BP#7
[7 empty] | 23:14 |  |  |  | 2 | 2 | Shooting Stage 2 BP#8
[7 empty] | 23:15 |  |  |  | 2 | 3 | Shooting Stage 2 BP#9
[7 empty] | 23:17 |  |  |  | 2 | 4 | Shooting Stage 2 BP#10
[7 empty] | 23:18 |  |  |  | 2 | 5 | Shooting Stage 2 BP#11
[7 empty] | 23:20 | [5 empty] | WL coming out of hole
[7 empty] | 23:22 | [5 empty] | Stop DTS. Prepare next session for S02F (V.00006)
[7 empty] | 23:24 | [5 empty] | Continue to wait for WL to get out of hole and Frac to begin
[7 empty] | 23:36 | [5 empty] | Stop hDVS Acquisition
Day 3 (11-7-2015)
[7 empty] | 0:20 | [5 empty] | WL out of hole
[7 empty] | 0:28 | [5 empty] | Start DTS Data for S02F
[7 empty] | 0:32 | [5 empty] | Start hDVS
[7 empty] | 0:47 | [5 empty] | Having pump issue
[7 empty] | 1:22 | [5 empty] | Begin Frac Stage 2
[7 empty] | 1:24 | [5 empty] | Pumping 15 bpm
[7 empty] | 1:26 | [5 empty] | Add 15% Acid
[7 empty] | 1:30 | [5 empty] | Start Pad
[7 empty] | 1:34 | [5 empty] | Reduce BPM to 15
[7 empty] | 1:41 | [5 empty] | 35 bpm
[7 empty] | 1:44 | [5 empty] | 51 bpm
[7 empty] | 1:50 | [5 empty] | 70 bpm
[7 empty] | 1:54 | [5 empty] | 0.25 Proppant increase/85bpm
[7 empty] | 1:57 | [5 empty] | Increase Proppant to 0.5
[7 empty] | 2:01 | [5 empty] | 0.75 Proppant
[7 empty] | 2:06 | [5 empty] | 1.0 Proppant
[7 empty] | 2:13 | [5 empty] | 1.5 Proppant
[7 empty] | 2:23 | [5 empty] | 2.0 Proppant
[7 empty] | 2:30 | [5 empty] | Drop to 0.5 Proppant
[7 empty] | 2:36 | [5 empty] | 0.75 Proppant
[7 empty] | 2:41 | [5 empty] | 1.0 Proppant
[7 empty] | 2:47 | [5 empty] | 90 bpm/1.5 Proppant
[7 empty] | 2:53 | [5 empty] | 2.0 Proppant
[7 empty] | 3:09 | [5 empty] | Proppant 0/75 bpm
[7 empty] | 3:12 | [5 empty] | Flush Out
[7 empty] | 3:14 | [5 empty] | 50 bpm
[7 empty] | 3:15 | [5 empty] | Stage 2 Complete. Stop DTS Acquisition
[7 empty] | 3:20 | [5 empty] | Prepare Ultra Session SO3P (v.00007)
[7 empty] | 3:46 | [5 empty] | WL Pressure Testing Lubricator. Start DTS Acquisition
[7 empty] | 3:55 | [5 empty] | WL Running Perf Guns for Stage 3
[7 empty] | 4:31 | [5 empty] | Pump down
[7 empty] | 4:53 | [5 empty] | Stop Pump Down/Pull up to correalate
[7 empty] | 4:58 | [5 empty] | Pump down
[7 empty] | 5:01 | [5 empty] | Stop Pump Down
[7 empty] | 5:06 | [5 empty] | Plug Set
[7 empty] | 5:14 |  |  |  | 3 | 1 | Shooting Stage 3 BP#12
[7 empty] | 5:16 | [5 empty] | Pump to orient Guns
[7 empty] | 5:37 |  |  |  | 3 | 2 | Shooting Stage 3 BP#13
[7 empty] | 5:42 |  |  |  | 3 | 3 | Shooting Stage 3 BP#14
[7 empty] | 5:44 |  |  |  | 3 | 4 | Shooting Stage 3 BP#15
[7 empty] | 5:45 | [5 empty] | Pump to orient Guns
[7 empty] | 5:48 |  |  |  | 3 | 5 | Shooting Stage 3 BP#16
[7 empty] | 5:49 | [5 empty] | WL coming out of hole. Stop DTS Acquisition
[7 empty] | 5:50 | [5 empty] | Prepare Ultra Session for S03F (v.00008)
[7 empty] | 7:48 |  |  |  | 3 |  | Stage 3 Frac started pump down 15 B/M
[7 empty] | 8:12 | [5 empty] | Increasing rate to 40 B/M
[7 empty] | 8:14 | [5 empty] | Rate at 60 B/M
[7 empty] | 8:15 | [5 empty] | Ten minutes until starting to pump sand
[7 empty] | 8:17 | [5 empty] | Rate at 65 B/M
[7 empty] | 8:19 | [5 empty] | 5 mins until sand and 1 1/2 hr until flush
[7 empty] | 8:19 | [5 empty] | Rate at 83 B/M
[7 empty] | 8:22 | [5 empty] | Rate at 90 B/M
[7 empty] | 8:23 | [5 empty] | Starting Sand
[7 empty] | 8:26 | [5 empty] | Prop at .25 PPAC
[7 empty] | 8:27 | [5 empty] | .5 PPAC at 90 B/M
[7 empty] | 8:31 | [5 empty] | .75 PPAC at 90 B/M
[7 empty] | 8:36 | [5 empty] | 1.0 PPAC at 90 B/M
[7 empty] | 8:42 | [5 empty] | 1.5 PPAC at 90 B/M
[7 empty] | 8:45 | [5 empty] | 1 hour until flush
[7 empty] | 8:52 | [5 empty] | 2.0 PPAC at 90 B/M
[7 empty] | 9:01 | [5 empty] | .5 PPAC at 90 B/M
[7 empty] | 9:07 | [5 empty] | .75 PPAC at 90 B/M
[7 empty] | 9:12 | [5 empty] | 1.0 PPAC at 90 B/M
[7 empty] | 9:17 | [5 empty] | 1.5 PPAC at 90 B/M
[7 empty] | 9:29 | [5 empty] | 2.0 PPAC at 90 B/M
[7 empty] | 9:49 | [5 empty] | Cutting sand at box
[7 empty] | 9:50 | [5 empty] | 0.0 PPAC
[7 empty] | 9:50 | [5 empty] | Flushing
[7 empty] | 9:55 | [5 empty] | Pumps off
[7 empty] | 10:10 | [5 empty] | Stopped DTS/HDVS Acquisition
[7 empty] | 10:11 | [5 empty] | Creating Session for Stage 4 Perf (NNE_MW3H_TW3H_S04P Version:9
[7 empty] | 10:30 |  |  |  | 4 |  | WL Pressure Testing Lubricator. Start DTS Acquisition
[7 empty] | 10:51 |  |  |  | 4 |  |  | Finished pressure testing
[7 empty] | 11:31 |  |  |  | 4 |  | WL lost communication with WPP tool, coming out of hole
[7 empty] | 13:18 |  |  |  | 4 |  | WL Pressure Testing Lubricator
[7 empty] | 13:30 |  |  |  | 4 |  | Wireline running perf guns
[7 empty] | 13:57 |  |  |  | 4 |  | Pumping guns down 2 B/M
[7 empty] | 14:00 |  |  |  | 4 |  | increase rate to 10 B/M
[7 empty] | 14:00 |  |  |  | 4 |  | Increase rate to 12 B/M
[7 empty] | 14:01 |  |  |  | 4 |  | Increase rate to 14 B/M
[7 empty] | 14:02 |  |  |  | 4 |  | Increase rate to 16 b/m
[7 empty] | 14:19 | [5 empty] | Stopped pumping down
[7 empty] | 14:45 | [5 empty] | Resume pump down, 2 B/M
[7 empty] | 14:45 | [5 empty] | Increase to 8 B/M
[7 empty] | 14:46 | [5 empty] | Increase to 14 B/M
[7 empty] | 14:48 | [5 empty] | Stopped pumping
[7 empty] | 14:51 | [5 empty] | WL logging
[7 empty] | 15:15 | [5 empty] | Resume pump down, 2 B/M
[7 empty] | 16:16 | [5 empty] | 14 B/M
[7 empty] | 15:19 | [5 empty] | Stopped pumping
[7 empty] | 15:20 | [5 empty] | Setting plug
[7 empty] | 15:22 | [5 empty] | Plug set
[7 empty] | 15:24 | [5 empty] | Pump on to move tool
[7 empty] | 15:26 | [5 empty] | Increase to 8 B/M
[7 empty] | 15:27 | [5 empty] | Stop pumping to pull up and pump back down
[7 empty] | 15:28 | [5 empty] | Pumping down
[7 empty] | 15:30 | [5 empty] | Stopped pumping
[7 empty] | 15:32 | [5 empty] | Pumping down
[7 empty] | 15:34 | [5 empty] | Stopped pumping
[7 empty] | 15:38 |  |  |  | 4 | 1 | shot Cluster #1 BP# 17
[7 empty] | 15:41 |  |  |  | 4 | 2 | Shot cluster #2 BP#18
[7 empty] | 15:43 |  |  |  | 4 | 3 | Shot cluster #3 BP#19
[7 empty] | 15:46 |  |  |  | 4 |  |  | Pumping down
[7 empty] | 15:49 |  |  |  | 4 |  |  | Stopped pumping
[7 empty] | 15:52 |  |  |  | 4 |  | Pumping down
[7 empty] | 16:10 |  |  |  | 4 |  | Stopped pumping
[7 empty] | 16:14 |  |  |  | 4 | 4 | Shot cluster #4 BP #20
[7 empty] | 16:16 |  |  |  | 4 | 5 | Shot cluster #5 BP #21
[7 empty] | 16:17 | [5 empty] | WL POOH
[7 empty] | 16:18 | [5 empty] | Stopped DTS and Wellsync
[7 empty] | 16:19 | [5 empty] | Preparing DTS session Version 10
[7 empty] | 16:34 | [5 empty] | Testing pumps
[7 empty] | 17:20 | [5 empty] | Started DTS and Wellsync
[7 empty] | 17:46 | [5 empty] | Starting stage 4 frac
[7 empty] | 17:47 | [5 empty] | pumping at 6 B/M
[7 empty] | 17:50 | [5 empty] | Swapping pumps, pumping stopped
[7 empty] | 17:53 | [5 empty] | Pumping down
[7 empty] | 17:54 | [5 empty] | at 10 B/M
[7 empty] | 17:55 | [5 empty] | at 15 B/M
[7 empty] | 17:57 | [5 empty] | Start Acid 7.5%
[7 empty] | 17:59 | [5 empty] | Start Spacer
[7 empty] | 18:00 | [5 empty] | Start Acid 7.5%
[7 empty] | 18:02 | [5 empty] | Start Pad
[7 empty] | 18:04 | [5 empty] | Stop Pump
[7 empty] | 18:07 | [5 empty] | Start pumping again/15bpm
[7 empty] | 18:17 | [5 empty] | 48bpm
[7 empty] | 18:19 | [5 empty] | 57bpm
[7 empty] | 18:20 | [5 empty] | 65bpm
[7 empty] | 18:21 | [5 empty] | 75bpm
[7 empty] | 18:24 | [5 empty] | 86bpm
[7 empty] | 18:28 | [5 empty] | 0.25 Proppant increase/90bpm
[7 empty] | 18:32 | [5 empty] | 0.50 Proppant
[7 empty] | 18:35 | [5 empty] | 0.75 Proppant
[7 empty] | 18:40 | [5 empty] | 1.0 Proppant
[7 empty] | 18:47 | [5 empty] | 1.5 Proppant
[7 empty] | 18:55 | [5 empty] | 2.0 Proppant
[7 empty] | 19:05 | [5 empty] | 0.5 Proppant
[7 empty] | 19:11 | [5 empty] | 0.75 Proppant
[7 empty] | 19:16 | [5 empty] | 1.0 Proppant
[7 empty] | 19:21 | [5 empty] | 1.5 Proppant
[7 empty] | 19:30 | [5 empty] | 2.0 Proppant
[7 empty] | 19:58 | [5 empty] | 2.5 Proppant/86bpm
[7 empty] | 19:59 | [5 empty] | 0 Proppant/Flush
[7 empty] | 20:02 | [5 empty] | Stage 4 Frac Complete. Stop DTS and change Session to SO5P (v.00011)

## hDVS
Stage | Trace | Depth Offset | Blast # | Amplitute | Start Time Fluid Intake | Stop Time | Date
1 | 511 | 13625.8 | 6 | 1784 | 16:40 | 19:05 | 2015-11-06
1 | 514 | 13676.02 | 5 | 1240 | 16:40 | 19:05 | 2015-11-06
1 | 520 | 13776.46 | 3 | 901 | 16:40 | 19:05 | 2015-11-06
1 | 516 | 13709.5 | 4 | 1822 | 16:40 | 19:05 | 2015-11-06
2 | 508 | 13575.58 | 7 | 1226 | 1:22 | 3:15 | 2015-11-07
2 | 505 | 13525.36 | 8 | 1517 | 1:22 | 3:15 | 2015-11-07
2 | 503 | 13491.88 | 9 | 1367 | 1:22 | 3:15 | 2015-11-07
2 | 500 | 13441.66 | 10 | 1455 | 1:22 | 3:15 | 2015-11-07
2 | 497 | 13391.44 | 11 | 1757 | 1:22 | 3:15 | 2015-11-07
4 | 481 | 13123.6 | 17 | 651 | 17:46 | 20:02 | 2015-11-07
4 | 478 | 13073.38 | 18 | 1380 | 17:46 | 20:02 | 2015-11-07
4 | 475 | 13023.16 | 19 | 1647 | 17:46 | 20:02 | 2015-11-07
4 | 472 | 12972.94 | 20 | 1942 | 17:46 | 20:02 | 2015-11-07
4 | 470 | 12939.46 | 21 | 1969 | 17:46 | 20:02 | 2015-11-07
5071.66
5071.66
5071.66
5071.66
5071.66
5071.66
5071.66
5071.66